## Endpoint Implementation Status
ID | Namespace | Namespace Interface | Endpoint | Endpoint Function | Function Result | Status | Notes
1 | Account | ITMDBNamespaceAccount | Details (by Account ID) | GetDetails | ITMDBAccountDetails | Done
2 | Account | ITMDBNamespaceAccount | Details (by Session ID) | GetDetailsBySession | ITMDBAccountDetails | Done | Not documented
3 | Account | ITMDBNamespaceAccount | Add Favorite | SetFavorite | ITMDBAccountAddFavoriteResult | Done
4 | Account | ITMDBNamespaceAccount | Add to Watchlist | SetWatchlist | ITMDBAccountAddWatchlistResult | Done
5 | Account | ITMDBNamespaceAccount | Favorite Movies | GetFavoriteMovies | ITMDBMoviePage | TEST
6 | Account | ITMDBNamespaceAccount | Favorite TV | GetFavoriteTV | ITMDBTVSeriesPage | TEST
7 | Account | ITMDBNamespaceAccount | Lists | GetLists | ITMDBListPage | TEST
8 | Account | ITMDBNamespaceAccount | Rated Movies | GetRatedMovies | ITMDBRatedMoviePage | TEST
9 | Account | ITMDBNamespaceAccount | Rated TV | GetRatedTV | ITMDBRatedTVSeriesPage | TEST
10 | Account | ITMDBNamespaceAccount | Rated TV Episodes | GetRatedTVEpisodes | ITMDBRatedTVEpisodePage | TEST
11 | Account | ITMDBNamespaceAccount | Watchlist Movies | GetWatchlistMovies | ITMDBMoviePage | TEST
12 | Account | ITMDBNamespaceAccount | Watchlist TV | GetWatchlistTV | ITMDBTVSeriesPage | TEST
13 | Authentication | ITMDBNamespaceAuthentication | Create Guest Session | CreateGuestSession | ITMDBAuthGuestSessionResult | Done
14 | Authentication | ITMDBNamespaceAuthentication | Create Request Token | CreateRequestToken | ITMDBAuthRequestTokenResult | Done
15 | Authentication | ITMDBNamespaceAuthentication | Create Session | CreateSession | ITMDBAuthSessionResult | Done
16 | Authentication | ITMDBNamespaceAuthentication | Create Session (from v4 token) | CreateSessionv4 | ITMDBAuthSessionResult | TEST
17 | Authentication | ITMDBNamespaceAuthentication | Create Session (with login) | CreateSessionLogin | ITMDBAuthSessionResultLogin | Done
18 | Authentication | ITMDBNamespaceAuthentication | Delete Session | DeleteSession | ITMDBAuthDeleteSessionResult | Done
19 | Authentication | ITMDBNamespaceAuthentication | Validate Key | ValidateKey | ITMDBAuthValidateKeyResult | Done
20 | Certifications | ITMDBNamespaceCertifications | Movie Certifications | GetMovieCertifications | ITMDBCertificationCountries | Done
21 | Certifications | ITMDBNamespaceCertifications | TV Certifications | GetTVCertifications | ITMDBCertificationCountries | Done
22 | Changes | ITMDBNamespaceChanges | Movie List | GetMovieChanges | ITMDBChanges | TEST
23 | Changes | ITMDBNamespaceChanges | People List | GetPeopleChanges | ITMDBChanges | TEST
24 | Changes | ITMDBNamespaceChanges | TV List | GetTVChanges | ITMDBChanges | TEST
25 | Collections | ITMDBNamespaceCollections | Details | GetDetails | ITMDBCollectionDetail | Done
26 | Collections | ITMDBNamespaceCollections | Images | GetImages | ITMDBMediaImageGroup | Done
27 | Collections | ITMDBNamespaceCollections | Translations | GetTranslations | ITMDBTranslations | TEST
28 | Companies | ITMDBNamespaceCompanies | Details | GetDetails | ITMDBCompanyDetail | TEST
29 | Companies | ITMDBNamespaceCompanies | Alternative Names | GetAlternativeNames | ITMDBAlternativeTitles | TEST
30 | Companies | ITMDBNamespaceCompanies | Images | GetImages | ITMDBMediaImageGroup | TEST
31 | Configuration | ITMDBNamespaceConfiguration | Details | GetDetails | ITMDBConfiguration | Done
32 | Configuration | ITMDBNamespaceConfiguration | Countries | GetCountries | ITMDBCountries | Done
33 | Configuration | ITMDBNamespaceConfiguration | Jobs | GetJobs | ITMDBJobDepartments | TEST
34 | Configuration | ITMDBNamespaceConfiguration | Languages | GetLanguages | ITMDBLanguages | Done
35 | Configuration | ITMDBNamespaceConfiguration | Primary Translations | GetPrimaryTranslations | TTMDBStrArray | Done
36 | Configuration | ITMDBNamespaceConfiguration | Timezones | GetTimezones | ITMDBTimezones | TEST
37 | Credits | ITMDBNamespaceCredits | Details | GetDetails | ITMDBCreditDetail | TEST
38 | Discover | ITMDBNamespaceDiscover | Movie | DiscoverMovies | ITMDBMoviePage | TEST | HUGE
39 | Discover | ITMDBNamespaceDiscover | TV | DiscoverTV | ITMDBTVSeriesPage | TEST | HUGE
40 | Find | ITMDBNamespaceFind | Find by ID | FindByID | ITMDBFindResults | TEST
41 | Genres | ITMDBNamespaceGenres | Movie List | GetMovieList | ITMDBGenres | Done
42 | Genres | ITMDBNamespaceGenres | TV List | GetTVList | ITMDBGenres | Done
43 | Guest Sessions | ITMDBNamespaceGuestSessions | Rated Movies | GetRatedMovies | ITMDBRatedMoviePage | TEST
44 | Guest Sessions | ITMDBNamespaceGuestSessions | Rated TV | GetRatedTV | ITMDBRatedTVSeriesPage | TEST
45 | Guest Sessions | ITMDBNamespaceGuestSessions | Rated TV Episodes | GetRatedTVEpisodes | ITMDBRatedTVEpisodePage | TEST
46 | Keywords | ITMDBNamespaceKeywords | Details | GetDetails | ITMDBKeywordDetail | TEST
47 | Keywords | ITMDBNamespaceKeywords | Movies (DEPRECATED) | GetMovies |  | TODO
48 | Lists | ITMDBNamespaceLists | Add Movie | AddMovie |  | TODO
49 | Lists | ITMDBNamespaceLists | Check Item Status | CheckItemStatus |  | TODO
50 | Lists | ITMDBNamespaceLists | Clear | Clear |  | TODO
51 | Lists | ITMDBNamespaceLists | Create | Create |  | TODO
52 | Lists | ITMDBNamespaceLists | Delete | Delete |  | TODO
53 | Lists | ITMDBNamespaceLists | Details | GetDetails | ITMDBListDetail | TODO
54 | Lists | ITMDBNamespaceLists | Remove Movie | RemoveMovie |  | TODO
55 | Movie Lists | ITMDBNamespaceMovieLists | Now Playing | GetNowPlaying | ITMDBDatedMoviePage | TEST
56 | Movie Lists | ITMDBNamespaceMovieLists | Popular | GetPopular | ITMDBMoviePage | TEST
57 | Movie Lists | ITMDBNamespaceMovieLists | Top Rated | GetTopRated | ITMDBMoviePage | TEST
58 | Movie Lists | ITMDBNamespaceMovieLists | Upcoming | GetUpcoming | ITMDBDatedMoviePage | TEST
59 | Movies | ITMDBNamespaceMovies | Details | GetDetails | ITMDBMovieDetail | TEST
60 | Movies | ITMDBNamespaceMovies | Account States | GetAccountStates | ITMDBAccountStates | TEST
61 | Movies | ITMDBNamespaceMovies | Alternative Titles | GetAlternativeTitles | ITMDBAlternativeTitles | Done
62 | Movies | ITMDBNamespaceMovies | Changes | GetChanges | ITMDBChanges | TEST
63 | Movies | ITMDBNamespaceMovies | Credits | GetCredits | ITMDBCredits | Done
64 | Movies | ITMDBNamespaceMovies | External IDs | GetExternalIDs | ITMDBExternalIDs | Done
65 | Movies | ITMDBNamespaceMovies | Images | GetImages | ITMDBMediaImageGroup | Done
66 | Movies | ITMDBNamespaceMovies | Keywords | GetKeywords | ITMDBKeywords | Done
67 | Movies | ITMDBNamespaceMovies | Latest | GetLatest | ITMDBMovieDetail | TEST
68 | Movies | ITMDBNamespaceMovies | Lists | GetLists | ITMDBListPage | TEST
69 | Movies | ITMDBNamespaceMovies | Recommendations | GetRecommendations | ITMDBMediaPage | TEST
70 | Movies | ITMDBNamespaceMovies | Release Dates | GetReleaseDates | ITMDBReleaseDateCountries | Done
71 | Movies | ITMDBNamespaceMovies | Reviews | GetReviews | ITMDBReviewPage | TEST
72 | Movies | ITMDBNamespaceMovies | Similar | GetSimilar | ITMDBMoviePage | TEST
73 | Movies | ITMDBNamespaceMovies | Translations | GetTranslations | ITMDBTranslations | Done
74 | Movies | ITMDBNamespaceMovies | Videos | GetVideos | ITMDBVideos | Done
75 | Movies | ITMDBNamespaceMovies | Watch Providers | GetWatchProviders | ITMDBMediaWatchProviders | TODO
76 | Movies | ITMDBNamespaceMovies | Add Rating | AddRating | ITMDBAddRatingResult | TODO
77 | Movies | ITMDBNamespaceMovies | Delete Rating | DeleteRating | ITMDBDeleteRatingResult | TODO
78 | Networks | ITMDBNamespaceNetworks | Details | GetDetails | ITMDBTVNetworkDetail | TEST
79 | Networks | ITMDBNamespaceNetworks | Alternative Names | GetAlternativeNames | ITMDBAlternativeTitles | TEST
80 | Networks | ITMDBNamespaceNetworks | Images | GetImages | ITMDBMediaImageGroup | TEST
81 | People Lists | ITMDBNamespacePeopleLists | Popular | GetPopular | ITMDBPersonPage | TEST
82 | People | ITMDBNamespacePeople | Details | GetDetails | ITMDBPersonDetail | TEST
83 | People | ITMDBNamespacePeople | Changes | GetChanges | ITMDBChanges | TEST
84 | People | ITMDBNamespacePeople | Combined Credits | GetCombinedCredits | ITMDBCombinedCredits | TEST
85 | People | ITMDBNamespacePeople | External IDs | GetExternalIDs | ITMDBExternalIDs | TEST
86 | People | ITMDBNamespacePeople | Images | GetImages | ITMDBMediaImageGroup | TEST
87 | People | ITMDBNamespacePeople | Latest | GetLatest | ITMDBPersonDetail | TEST
88 | People | ITMDBNamespacePeople | Movie Credits | GetMovieCredits | ITMDBCombinedCredits | TEST
89 | People | ITMDBNamespacePeople | TV Credits | GetTVCredits | ITMDBCombinedCredits | TEST
90 | People | ITMDBNamespacePeople | Tagged Images (DEPRECATED) | GetTaggedImages |  | TODO
91 | People | ITMDBNamespacePeople | Translations | GetTranslations | ITMDBTranslations | TEST
92 | Reviews | ITMDBNamespaceReviews | Details | GetDetails | ITMDBReviewDetail | TEST
93 | Search | ITMDBNamespaceSearch | Collection | SearchCollections | ITMDBCollectionPage | Done
94 | Search | ITMDBNamespaceSearch | Company | SearchCompanies | ITMDBCompanyPage | Done
95 | Search | ITMDBNamespaceSearch | Keyword | SearchKeywords | ITMDBKeywordPage | Done
96 | Search | ITMDBNamespaceSearch | Movie | SearchMovies | ITMDBMoviePage | Done
97 | Search | ITMDBNamespaceSearch | Multi | SearchMulti | ITMDBMediaPage | Done
98 | Search | ITMDBNamespaceSearch | Person | SearchPeople | ITMDBPersonPage | Done
99 | Search | ITMDBNamespaceSearch | TV | SearchTV | ITMDBTVSeriesPage | Done
100 | Trending | ITMDBNamespaceTrending | All | GetAll | ITMDBMediaPage | TEST
101 | Trending | ITMDBNamespaceTrending | Movies | GetMovies | ITMDBMoviePage | TEST
102 | Trending | ITMDBNamespaceTrending | People | GetPeople | ITMDBPersonPage | TEST
103 | Trending | ITMDBNamespaceTrending | TV | GetTV | ITMDBTVSeriesPage | TEST
104 | TV Series Lists | ITMDBNamespaceTVSeriesLists | Airing Today | GetAiringToday | ITMDBTVSeriesPage | TEST
105 | TV Series Lists | ITMDBNamespaceTVSeriesLists | On The Air | GetOnTheAir | ITMDBTVSeriesPage | TEST
106 | TV Series Lists | ITMDBNamespaceTVSeriesLists | Popular | GetPopular | ITMDBTVSeriesPage | TEST
107 | TV Series Lists | ITMDBNamespaceTVSeriesLists | Top Rated | GetTopRated | ITMDBTVSeriesPage | TEST
108 | TV Series | ITMDBNamespaceTVSeries | Details | GetDetails | ITMDBTVSeriesDetail | IN PROGRESS | Need to finish Append-to-Response data
109 | TV Series | ITMDBNamespaceTVSeries | Account States | GetAccountStates | ITMDBAccountStates | TEST
110 | TV Series | ITMDBNamespaceTVSeries | Aggregate Credits | GetAggregateCredits | ITMDBAggregateCredits | TEST
111 | TV Series | ITMDBNamespaceTVSeries | Alternative Titles | GetAlternativeTitles | ITMDBAlternativeTitles | TEST
112 | TV Series | ITMDBNamespaceTVSeries | Changes | GetChanges | ITMDBChanges | TEST
113 | TV Series | ITMDBNamespaceTVSeries | Content Ratings | GetContentRatings | ITMDBContentRatings | TEST
114 | TV Series | ITMDBNamespaceTVSeries | Credits | GetCredits | ITMDBCredits | TEST
115 | TV Series | ITMDBNamespaceTVSeries | Episode Groups | GetEpisodeGroups | ITMDBEpisodeGroups | TEST
116 | TV Series | ITMDBNamespaceTVSeries | External IDs | GetExternalIDs | ITMDBExternalIDs | TEST
117 | TV Series | ITMDBNamespaceTVSeries | Images | GetImages | ITMDBMediaImageGroup | TEST
118 | TV Series | ITMDBNamespaceTVSeries | Keywords | GetKeywords | ITMDBKeywords | TEST
119 | TV Series | ITMDBNamespaceTVSeries | Latest | GetLatest | ITMDBTVSeriesDetail | TEST
120 | TV Series | ITMDBNamespaceTVSeries | Lists | GetLists | ITMDBListPage | TEST
121 | TV Series | ITMDBNamespaceTVSeries | Recommendations | GetRecommendations | ITMDBTVSeriesPage | TEST
122 | TV Series | ITMDBNamespaceTVSeries | Reviews | GetReviews | ITMDBReviews | TEST
123 | TV Series | ITMDBNamespaceTVSeries | Screened Theatrically | GetScreenedTheatrically |  | TEST
124 | TV Series | ITMDBNamespaceTVSeries | Similar | GetSimilar | ITMDBTVSeriesPage | TEST
125 | TV Series | ITMDBNamespaceTVSeries | Translations | GetTranslations | ITMDBTranslations | TEST
126 | TV Series | ITMDBNamespaceTVSeries | Videos | GetVideos | ITMDBVideos | TEST
127 | TV Series | ITMDBNamespaceTVSeries | Watch Providers | GetWatchProviders | ITMDBMediaWatchProviders | TODO
128 | TV Series | ITMDBNamespaceTVSeries | Add Rating | AddRating |  | TODO
129 | TV Series | ITMDBNamespaceTVSeries | Delete Rating | DeleteRating |  | TODO
130 | TV Seasons | ITMDBNamespaceTVSeasons | Details | GetDetail | ITMDBTVSeasonDetail | TEST
131 | TV Seasons | ITMDBNamespaceTVSeasons | Account States | GetAccountStates | ITMDBAccountStates | TEST
132 | TV Seasons | ITMDBNamespaceTVSeasons | Aggregate Credits | GetAggregateCredits | ITMDBAggregateCredits | TEST
133 | TV Seasons | ITMDBNamespaceTVSeasons | Changes | GetChanges | ITMDBChanges | TEST
134 | TV Seasons | ITMDBNamespaceTVSeasons | Credits | GetCredits | ITMDBCredits | TEST
135 | TV Seasons | ITMDBNamespaceTVSeasons | External IDs | GetExternalIDs | ITMDBExternalIDs | TEST
136 | TV Seasons | ITMDBNamespaceTVSeasons | Images | GetImages | ITMDBMediaImageGroup | TEST
137 | TV Seasons | ITMDBNamespaceTVSeasons | Translations | GetTranslations | ITMDBTranslations | TEST
138 | TV Seasons | ITMDBNamespaceTVSeasons | Videos | GetVideos | ITMDBVideos | TEST
139 | TV Seasons | ITMDBNamespaceTVSeasons | Watch Providers | GetWatchProviders | ITMDBMediaWatchProviders | TODO
140 | TV Episodes | ITMDBNamespaceTVEpisodes | Details | GetDetail | ITMDBEpisodeDetail | TEST
141 | TV Episodes | ITMDBNamespaceTVEpisodes | Account States | GetAccountStates | ITMDBAccountStates | TEST
142 | TV Episodes | ITMDBNamespaceTVEpisodes | Changes | GetChanges | ITMDBChanges | TEST
143 | TV Episodes | ITMDBNamespaceTVEpisodes | Credits | GetCredits | ITMDBCredits | TEST
144 | TV Episodes | ITMDBNamespaceTVEpisodes | External IDs | GetExternalIDs | ITMDBExternalIDs | TEST
145 | TV Episodes | ITMDBNamespaceTVEpisodes | Images | GetImages | ITMDBMediaImageGroup | TEST
146 | TV Episodes | ITMDBNamespaceTVEpisodes | Translations | GetTranslations | ITMDBTranslations | TEST
147 | TV Episodes | ITMDBNamespaceTVEpisodes | Videos | GetVideos | ITMDBVideos | TEST
148 | TV Episodes | ITMDBNamespaceTVEpisodes | Add Rating | AddRating |  | TODO
149 | TV Episodes | ITMDBNamespaceTVEpisodes | Delete Rating | DeleteRating |  | TODO
150 | TV Episode Groups | ITMDBNamespaceTVEpisodeGroups | Details | GetDetails | ITMDBTVEpisodeGroups | TEST
151 | Watch Providers | ITMDBNamespaceWatchProviders | Available Regions | GetAvailableRegions | ITMDBCountries | TEST
152 | Watch Providers | ITMDBNamespaceWatchProviders | Movie Providers | GetMovieProviders | ITMDBWatchProviders | TEST
153 | Watch Providers | ITMDBNamespaceWatchProviders | TV Providers | GetTVProviders | ITMDBWatchProviders | TEST

## Interface and Object List
Category | Name | Ancestor | Intf Stat | Impl Stat | App Stat | Interface Name | Object Name | Interface Forward Definition | Object Forward Definition | Interface Definition | Object Definition | Base
Common | Item |  | DONE | DONE | DONE | ITMDBItem | TTMDBItem | ITMDBItem = interface; | TTMDBItem = class; | ITMDBItem = interface | TTMDBItem = class(TInterfacedObject, ITMDBItem) | TMDB
Common | Items |  | DONE | DONE | DONE | ITMDBItems | TTMDBItems | ITMDBItems = interface; | TTMDBItems = class; | ITMDBItems = interface | TTMDBItems = class(TInterfacedObject, ITMDBItems) | TMDB
Common | Page |  | DONE | DONE | DONE | ITMDBPage | TTMDBPage | ITMDBPage = interface; | TTMDBPage = class; | ITMDBPage = interface | TTMDBPage = class(TInterfacedObject, ITMDBPage) | TMDB
Common | Detail |  | DONE | DONE | DONE | ITMDBDetail | TTMDBDetail | ITMDBDetail = interface; | TTMDBDetail = class; | ITMDBDetail = interface | TTMDBDetail = class(TInterfacedObject, ITMDBDetail) | TMDB
Media | Medium | Item | DONE | DONE | DONE | ITMDBMedium | TTMDBMedium | ITMDBMedium = interface; | TTMDBMedium = class; | ITMDBMedium = interface(ITMDBItem) | TTMDBMedium = class(TTMDBItem, ITMDBMedium) | TMDB
Media | Media | Items | DONE | DONE | DONE | ITMDBMedia | TTMDBMedia | ITMDBMedia = interface; | TTMDBMedia = class; | ITMDBMedia = interface(ITMDBItems) | TTMDBMedia = class(TTMDBItems, ITMDBMedia) | TMDB
Media | MediaPage | Page | DONE | DONE | DONE | ITMDBMediaPage | TTMDBMediaPage | ITMDBMediaPage = interface; | TTMDBMediaPage = class; | ITMDBMediaPage = interface(ITMDBPage) | TTMDBMediaPage = class(TTMDBPage, ITMDBMediaPage) | TMDB
Account | AccountDetail |  | DONE | DONE | DONE | ITMDBAccountDetail | TTMDBAccountDetail | ITMDBAccountDetail = interface; | TTMDBAccountDetail = class; | ITMDBAccountDetail = interface | TTMDBAccountDetail = class(TInterfacedObject, ITMDBAccountDetail) | TMDB
Account | AccountAddFavoriteResult |  | DONE | DONE | DONE | ITMDBAccountAddFavoriteResult | TTMDBAccountAddFavoriteResult | ITMDBAccountAddFavoriteResult = interface; | TTMDBAccountAddFavoriteResult = class; | ITMDBAccountAddFavoriteResult = interface | TTMDBAccountAddFavoriteResult = class(TInterfacedObject, ITMDBAccountAddFavoriteResult) | TMDB
Account | AccountAddWatchlistResult |  | DONE | DONE | DONE | ITMDBAccountAddWatchlistResult | TTMDBAccountAddWatchlistResult | ITMDBAccountAddWatchlistResult = interface; | TTMDBAccountAddWatchlistResult = class; | ITMDBAccountAddWatchlistResult = interface | TTMDBAccountAddWatchlistResult = class(TInterfacedObject, ITMDBAccountAddWatchlistResult) | TMDB
Account | AccountStates |  | DONE | DONE | DONE | ITMDBAccountStates | TTMDBAccountStates | ITMDBAccountStates = interface; | TTMDBAccountStates = class; | ITMDBAccountStates = interface | TTMDBAccountStates = class(TInterfacedObject, ITMDBAccountStates) | TMDB
Authentication | AuthGuestSessionResult |  | DONE | DONE | DONE | ITMDBAuthGuestSessionResult | TTMDBAuthGuestSessionResult | ITMDBAuthGuestSessionResult = interface; | TTMDBAuthGuestSessionResult = class; | ITMDBAuthGuestSessionResult = interface | TTMDBAuthGuestSessionResult = class(TInterfacedObject, ITMDBAuthGuestSessionResult) | TMDB
Authentication | AuthRequestTokenResult |  | DONE | DONE | DONE | ITMDBAuthRequestTokenResult | TTMDBAuthRequestTokenResult | ITMDBAuthRequestTokenResult = interface; | TTMDBAuthRequestTokenResult = class; | ITMDBAuthRequestTokenResult = interface | TTMDBAuthRequestTokenResult = class(TInterfacedObject, ITMDBAuthRequestTokenResult) | TMDB
Authentication | AuthSessionResult |  | DONE | DONE | DONE | ITMDBAuthSessionResult | TTMDBAuthSessionResult | ITMDBAuthSessionResult = interface; | TTMDBAuthSessionResult = class; | ITMDBAuthSessionResult = interface | TTMDBAuthSessionResult = class(TInterfacedObject, ITMDBAuthSessionResult) | TMDB
Authentication | AuthSessionResultLogin |  | DONE | DONE | DONE | ITMDBAuthSessionResultLogin | TTMDBAuthSessionResultLogin | ITMDBAuthSessionResultLogin = interface; | TTMDBAuthSessionResultLogin = class; | ITMDBAuthSessionResultLogin = interface | TTMDBAuthSessionResultLogin = class(TInterfacedObject, ITMDBAuthSessionResultLogin) | TMDB
Authentication | AuthDeleteSessionResult |  | DONE | DONE | DONE | ITMDBAuthDeleteSessionResult | TTMDBAuthDeleteSessionResult | ITMDBAuthDeleteSessionResult = interface; | TTMDBAuthDeleteSessionResult = class; | ITMDBAuthDeleteSessionResult = interface | TTMDBAuthDeleteSessionResult = class(TInterfacedObject, ITMDBAuthDeleteSessionResult) | TMDB
Authentication | AuthValidateKeyResult |  | DONE | DONE | DONE | ITMDBAuthValidateKeyResult | TTMDBAuthValidateKeyResult | ITMDBAuthValidateKeyResult = interface; | TTMDBAuthValidateKeyResult = class; | ITMDBAuthValidateKeyResult = interface | TTMDBAuthValidateKeyResult = class(TInterfacedObject, ITMDBAuthValidateKeyResult) | TMDB
Alternative Titles | AlternativeTitle | Item | DONE | DONE | DONE | ITMDBAlternativeTitle | TTMDBAlternativeTitle | ITMDBAlternativeTitle = interface; | TTMDBAlternativeTitle = class; | ITMDBAlternativeTitle = interface(ITMDBItem) | TTMDBAlternativeTitle = class(TTMDBItem, ITMDBAlternativeTitle) | TMDB
Alternative Titles | AlternativeTitles | Items | DONE | DONE | DONE | ITMDBAlternativeTitles | TTMDBAlternativeTitles | ITMDBAlternativeTitles = interface; | TTMDBAlternativeTitles = class; | ITMDBAlternativeTitles = interface(ITMDBItems) | TTMDBAlternativeTitles = class(TTMDBItems, ITMDBAlternativeTitles) | TMDB
Certifications | Certification |  | DONE | DONE | DONE | ITMDBCertification | TTMDBCertification | ITMDBCertification = interface; | TTMDBCertification = class; | ITMDBCertification = interface | TTMDBCertification = class(TInterfacedObject, ITMDBCertification) | TMDB
Certifications | CertificationCountry |  | DONE | DONE | DONE | ITMDBCertificationCountry | TTMDBCertificationCountry | ITMDBCertificationCountry = interface; | TTMDBCertificationCountry = class; | ITMDBCertificationCountry = interface | TTMDBCertificationCountry = class(TInterfacedObject, ITMDBCertificationCountry) | TMDB
Certifications | CertificationCountries |  | DONE | DONE | DONE | ITMDBCertificationCountries | TTMDBCertificationCountries | ITMDBCertificationCountries = interface; | TTMDBCertificationCountries = class; | ITMDBCertificationCountries = interface | TTMDBCertificationCountries = class(TInterfacedObject, ITMDBCertificationCountries) | TMDB
Changes | ChangeValue |  | DONE | DONE | TODO | ITMDBChangeValue | TTMDBChangeValue | ITMDBChangeValue = interface; | TTMDBChangeValue = class; | ITMDBChangeValue = interface | TTMDBChangeValue = class(TInterfacedObject, ITMDBChangeValue) | TMDB
Changes | ChangeRecord |  | DONE | DONE | TODO | ITMDBChangeRecord | TTMDBChangeRecord | ITMDBChangeRecord = interface; | TTMDBChangeRecord = class; | ITMDBChangeRecord = interface | TTMDBChangeRecord = class(TInterfacedObject, ITMDBChangeRecord) | TMDB
Changes | Change | Item | DONE | DONE | TODO | ITMDBChange | TTMDBChange | ITMDBChange = interface; | TTMDBChange = class; | ITMDBChange = interface(ITMDBItem) | TTMDBChange = class(TTMDBItem, ITMDBChange) | TMDB
Changes | Changes | Items | DONE | DONE | TODO | ITMDBChanges | TTMDBChanges | ITMDBChanges = interface; | TTMDBChanges = class; | ITMDBChanges = interface(ITMDBItems) | TTMDBChanges = class(TTMDBItems, ITMDBChanges) | TMDB
Changes | ChangeRef | Item | DONE | DONE | TODO | ITMDBChangeRef | TTMDBChangeRef | ITMDBChangeRef = interface; | TTMDBChangeRef = class; | ITMDBChangeRef = interface(ITMDBItem) | TTMDBChangeRef = class(TTMDBItem, ITMDBChangeRef) | TMDB
Changes | ChangeRefs | Items | DONE | DONE | TODO | ITMDBChangeRefs | TTMDBChangeRefs | ITMDBChangeRefs = interface; | TTMDBChangeRefs = class; | ITMDBChangeRefs = interface(ITMDBItems) | TTMDBChangeRefs = class(TTMDBItems, ITMDBChangeRefs) | TMDB
Changes | ChangeRefPage | Page | DONE | DONE | TODO | ITMDBChangeRefPage | TTMDBChangeRefPage | ITMDBChangeRefPage = interface; | TTMDBChangeRefPage = class; | ITMDBChangeRefPage = interface(ITMDBPage) | TTMDBChangeRefPage = class(TTMDBPage, ITMDBChangeRefPage) | TMDB
Companies | Company | Item | DONE | DONE | TEST | ITMDBCompany | TTMDBCompany | ITMDBCompany = interface; | TTMDBCompany = class; | ITMDBCompany = interface(ITMDBItem) | TTMDBCompany = class(TTMDBItem, ITMDBCompany) | TMDB
Companies | Companies | Items | DONE | DONE | TEST | ITMDBCompanies | TTMDBCompanies | ITMDBCompanies = interface; | TTMDBCompanies = class; | ITMDBCompanies = interface(ITMDBItems) | TTMDBCompanies = class(TTMDBItems, ITMDBCompanies) | TMDB
Companies | CompanyPage | Page | DONE | DONE | TEST | ITMDBCompanyPage | TTMDBCompanyPage | ITMDBCompanyPage = interface; | TTMDBCompanyPage = class; | ITMDBCompanyPage = interface(ITMDBPage) | TTMDBCompanyPage = class(TTMDBPage, ITMDBCompanyPage) | TMDB
Companies | CompanyDetail | Detail | DONE | DONE | TEST | ITMDBCompanyDetail | TTMDBCompanyDetail | ITMDBCompanyDetail = interface; | TTMDBCompanyDetail = class; | ITMDBCompanyDetail = interface(ITMDBDetail) | TTMDBCompanyDetail = class(TTMDBDetail, ITMDBCompanyDetail) | TMDB
Configuration | ConfigurationImages |  | DONE | DONE | TODO | ITMDBConfigurationImages | TTMDBConfigurationImages | ITMDBConfigurationImages = interface; | TTMDBConfigurationImages = class; | ITMDBConfigurationImages = interface | TTMDBConfigurationImages = class(TInterfacedObject, ITMDBConfigurationImages) | TMDB
Configuration | Configuration |  | DONE | DONE | TODO | ITMDBConfiguration | TTMDBConfiguration | ITMDBConfiguration = interface; | TTMDBConfiguration = class; | ITMDBConfiguration = interface | TTMDBConfiguration = class(TInterfacedObject, ITMDBConfiguration) | TMDB
Content Ratings | ContentRating | Item | DONE | DONE | TODO | ITMDBContentRating | TTMDBContentRating | ITMDBContentRating = interface; | TTMDBContentRating = class; | ITMDBContentRating = interface(ITMDBItem) | TTMDBContentRating = class(TTMDBItem, ITMDBContentRating) | TMDB
Content Ratings | ContentRatings | Items | DONE | DONE | TODO | ITMDBContentRatings | TTMDBContentRatings | ITMDBContentRatings = interface; | TTMDBContentRatings = class; | ITMDBContentRatings = interface(ITMDBItems) | TTMDBContentRatings = class(TTMDBItems, ITMDBContentRatings) | TMDB
Countries | Country | Item | DONE | DONE | DONE | ITMDBCountry | TTMDBCountry | ITMDBCountry = interface; | TTMDBCountry = class; | ITMDBCountry = interface(ITMDBItem) | TTMDBCountry = class(TTMDBItem, ITMDBCountry) | TMDB
Countries | Countries | Items | DONE | DONE | DONE | ITMDBCountries | TTMDBCountries | ITMDBCountries = interface; | TTMDBCountries = class; | ITMDBCountries = interface(ITMDBItems) | TTMDBCountries = class(TTMDBItems, ITMDBCountries) | TMDB
External IDs | ExternalIDs |  | DONE | DONE | TEST | ITMDBExternalIDs | TTMDBExternalIDs | ITMDBExternalIDs = interface; | TTMDBExternalIDs = class; | ITMDBExternalIDs = interface | TTMDBExternalIDs = class(TInterfacedObject, ITMDBExternalIDs) | TMDB
Genres | Genre | Item | DONE | DONE | DONE | ITMDBGenre | TTMDBGenre | ITMDBGenre = interface; | TTMDBGenre = class; | ITMDBGenre = interface(ITMDBItem) | TTMDBGenre = class(TTMDBItem, ITMDBGenre) | TMDB
Genres | Genres | Items | DONE | DONE | DONE | ITMDBGenres | TTMDBGenres | ITMDBGenres = interface; | TTMDBGenres = class; | ITMDBGenres = interface(ITMDBItems) | TTMDBGenres = class(TTMDBItems, ITMDBGenres) | TMDB
Images | MediaImage | Item | DONE | DONE | TEST | ITMDBMediaImage | TTMDBMediaImage | ITMDBMediaImage = interface; | TTMDBMediaImage = class; | ITMDBMediaImage = interface(ITMDBItem) | TTMDBMediaImage = class(TTMDBItem, ITMDBMediaImage) | TMDB
Images | MediaImages | Items | DONE | DONE | TEST | ITMDBMediaImages | TTMDBMediaImages | ITMDBMediaImages = interface; | TTMDBMediaImages = class; | ITMDBMediaImages = interface(ITMDBItems) | TTMDBMediaImages = class(TTMDBItems, ITMDBMediaImages) | TMDB
Images | MediaImageGroup |  | DONE | DONE | TEST | ITMDBMediaImageGroup | TTMDBMediaImageGroup | ITMDBMediaImageGroup = interface; | TTMDBMediaImageGroup = class; | ITMDBMediaImageGroup = interface | TTMDBMediaImageGroup = class(TInterfacedObject, ITMDBMediaImageGroup) | TMDB
Jobs | JobDepartment | Item | DONE | DONE | TEST | ITMDBJobDepartment | TTMDBJobDepartment | ITMDBJobDepartment = interface; | TTMDBJobDepartment = class; | ITMDBJobDepartment = interface(ITMDBItem) | TTMDBJobDepartment = class(TTMDBItem, ITMDBJobDepartment) | TMDB
Jobs | JobDepartments | Items | DONE | DONE | TEST | ITMDBJobDepartments | TTMDBJobDepartments | ITMDBJobDepartments = interface; | TTMDBJobDepartments = class; | ITMDBJobDepartments = interface(ITMDBItems) | TTMDBJobDepartments = class(TTMDBItems, ITMDBJobDepartments) | TMDB
Keywords | Keyword | Item | DONE | DONE | DONE | ITMDBKeyword | TTMDBKeyword | ITMDBKeyword = interface; | TTMDBKeyword = class; | ITMDBKeyword = interface(ITMDBItem) | TTMDBKeyword = class(TTMDBItem, ITMDBKeyword) | TMDB
Keywords | Keywords | Items | DONE | DONE | DONE | ITMDBKeywords | TTMDBKeywords | ITMDBKeywords = interface; | TTMDBKeywords = class; | ITMDBKeywords = interface(ITMDBItems) | TTMDBKeywords = class(TTMDBItems, ITMDBKeywords) | TMDB
Keywords | KeywordPage | Page | DONE | DONE | DONE | ITMDBKeywordPage | TTMDBKeywordPage | ITMDBKeywordPage = interface; | TTMDBKeywordPage = class; | ITMDBKeywordPage = interface(ITMDBPage) | TTMDBKeywordPage = class(TTMDBPage, ITMDBKeywordPage) | TMDB
Keywords | KeywordDetail | Detail | DONE | DONE | DONE | ITMDBKeywordDetail | TTMDBKeywordDetail | ITMDBKeywordDetail = interface; | TTMDBKeywordDetail = class; | ITMDBKeywordDetail = interface(ITMDBDetail) | TTMDBKeywordDetail = class(TTMDBDetail, ITMDBKeywordDetail) | TMDB
Languages | Language | Item | DONE | DONE | DONE | ITMDBLanguage | TTMDBLanguage | ITMDBLanguage = interface; | TTMDBLanguage = class; | ITMDBLanguage = interface(ITMDBItem) | TTMDBLanguage = class(TTMDBItem, ITMDBLanguage) | TMDB
Languages | Languages | Items | DONE | DONE | DONE | ITMDBLanguages | TTMDBLanguages | ITMDBLanguages = interface; | TTMDBLanguages = class; | ITMDBLanguages = interface(ITMDBItems) | TTMDBLanguages = class(TTMDBItems, ITMDBLanguages) | TMDB
Network | TVNetwork | Item | DONE | DONE | DONE | ITMDBTVNetwork | TTMDBTVNetwork | ITMDBTVNetwork = interface; | TTMDBTVNetwork = class; | ITMDBTVNetwork = interface(ITMDBItem) | TTMDBTVNetwork = class(TTMDBItem, ITMDBTVNetwork) | TMDB
Network | TVNetworks | Items | DONE | DONE | TEST | ITMDBTVNetworks | TTMDBTVNetworks | ITMDBTVNetworks = interface; | TTMDBTVNetworks = class; | ITMDBTVNetworks = interface(ITMDBItems) | TTMDBTVNetworks = class(TTMDBItems, ITMDBTVNetworks) | TMDB
Network | TVNetworkDetail | Detail | DONE | DONE | TEST | ITMDBTVNetworkDetail | TTMDBTVNetworkDetail | ITMDBTVNetworkDetail = interface; | TTMDBTVNetworkDetail = class; | ITMDBTVNetworkDetail = interface(ITMDBDetail) | TTMDBTVNetworkDetail = class(TTMDBDetail, ITMDBTVNetworkDetail) | TMDB
Timezones | Timezone | Item | DONE | DONE | TEST | ITMDBTimezone | TTMDBTimezone | ITMDBTimezone = interface; | TTMDBTimezone = class; | ITMDBTimezone = interface(ITMDBItem) | TTMDBTimezone = class(TTMDBItem, ITMDBTimezone) | TMDB
Timezones | Timezones | Items | DONE | DONE | TEST | ITMDBTimezones | TTMDBTimezones | ITMDBTimezones = interface; | TTMDBTimezones = class; | ITMDBTimezones = interface(ITMDBItems) | TTMDBTimezones = class(TTMDBItems, ITMDBTimezones) | TMDB
Release Dates | ReleaseDate |  | DONE | DONE | DONE | ITMDBReleaseDate | TTMDBReleaseDate | ITMDBReleaseDate = interface; | TTMDBReleaseDate = class; | ITMDBReleaseDate = interface | TTMDBReleaseDate = class(TInterfacedObject, ITMDBReleaseDate) | TMDB
Release Dates | ReleaseDateCountry |  | DONE | DONE | DONE | ITMDBReleaseDateCountry | TTMDBReleaseDateCountry | ITMDBReleaseDateCountry = interface; | TTMDBReleaseDateCountry = class; | ITMDBReleaseDateCountry = interface | TTMDBReleaseDateCountry = class(TInterfacedObject, ITMDBReleaseDateCountry) | TMDB
Release Dates | ReleaseDateCountries |  | DONE | DONE | DONE | ITMDBReleaseDateCountries | TTMDBReleaseDateCountries | ITMDBReleaseDateCountries = interface; | TTMDBReleaseDateCountries = class; | ITMDBReleaseDateCountries = interface | TTMDBReleaseDateCountries = class(TInterfacedObject, ITMDBReleaseDateCountries) | TMDB
Translations | TranslationData |  | DONE | DONE | TEST | ITMDBTranslationData | TTMDBTranslationData | ITMDBTranslationData = interface; | TTMDBTranslationData = class; | ITMDBTranslationData = interface | TTMDBTranslationData = class(TInterfacedObject, ITMDBTranslationData) | TMDB
Translations | MovieTranslationData | TranslationData | DONE | DONE | TEST | ITMDBMovieTranslationData | TTMDBMovieTranslationData | ITMDBMovieTranslationData = interface; | TTMDBMovieTranslationData = class; | ITMDBMovieTranslationData = interface(ITMDBTranslationData) | TTMDBMovieTranslationData = class(TTMDBTranslationData, ITMDBMovieTranslationData) | TMDB
Translations | CollectionTranslationData | TranslationData | DONE | DONE | TEST | ITMDBCollectionTranslationData | TTMDBCollectionTranslationData | ITMDBCollectionTranslationData = interface; | TTMDBCollectionTranslationData = class; | ITMDBCollectionTranslationData = interface(ITMDBTranslationData) | TTMDBCollectionTranslationData = class(TTMDBTranslationData, ITMDBCollectionTranslationData) | TMDB
Translations | PersonTranslationData | TranslationData | DONE | DONE | TEST | ITMDBPersonTranslationData | TTMDBPersonTranslationData | ITMDBPersonTranslationData = interface; | TTMDBPersonTranslationData = class; | ITMDBPersonTranslationData = interface(ITMDBTranslationData) | TTMDBPersonTranslationData = class(TTMDBTranslationData, ITMDBPersonTranslationData) | TMDB
Translations | TVSeriesTranslationData | TranslationData | DONE | DONE | TEST | ITMDBTVSeriesTranslationData | TTMDBTVSeriesTranslationData | ITMDBTVSeriesTranslationData = interface; | TTMDBTVSeriesTranslationData = class; | ITMDBTVSeriesTranslationData = interface(ITMDBTranslationData) | TTMDBTVSeriesTranslationData = class(TTMDBTranslationData, ITMDBTVSeriesTranslationData) | TMDB
Translations | TVSeasonTranslationData | TranslationData | DONE | DONE | TEST | ITMDBTVSeasonTranslationData | TTMDBTVSeasonTranslationData | ITMDBTVSeasonTranslationData = interface; | TTMDBTVSeasonTranslationData = class; | ITMDBTVSeasonTranslationData = interface(ITMDBTranslationData) | TTMDBTVSeasonTranslationData = class(TTMDBTranslationData, ITMDBTVSeasonTranslationData) | TMDB
Translations | TVEpisodeTranslationData | TranslationData | DONE | DONE | TEST | ITMDBTVEpisodeTranslationData | TTMDBTVEpisodeTranslationData | ITMDBTVEpisodeTranslationData = interface; | TTMDBTVEpisodeTranslationData = class; | ITMDBTVEpisodeTranslationData = interface(ITMDBTranslationData) | TTMDBTVEpisodeTranslationData = class(TTMDBTranslationData, ITMDBTVEpisodeTranslationData) | TMDB
Translations | Translation | Item | DONE | DONE | TEST | ITMDBTranslation | TTMDBTranslation | ITMDBTranslation = interface; | TTMDBTranslation = class; | ITMDBTranslation = interface(ITMDBItem) | TTMDBTranslation = class(TTMDBItem, ITMDBTranslation) | TMDB
Translations | Translations | Items | DONE | DONE | TEST | ITMDBTranslations | TTMDBTranslations | ITMDBTranslations = interface; | TTMDBTranslations = class; | ITMDBTranslations = interface(ITMDBItems) | TTMDBTranslations = class(TTMDBItems, ITMDBTranslations) | TMDB
Videos | Video | Item | DONE | DONE | DONE | ITMDBVideo | TTMDBVideo | ITMDBVideo = interface; | TTMDBVideo = class; | ITMDBVideo = interface(ITMDBItem) | TTMDBVideo = class(TTMDBItem, ITMDBVideo) | TMDB
Videos | Videos | Items | DONE | DONE | DONE | ITMDBVideos | TTMDBVideos | ITMDBVideos = interface; | TTMDBVideos = class; | ITMDBVideos = interface(ITMDBItems) | TTMDBVideos = class(TTMDBItems, ITMDBVideos) | TMDB
Collections | Collection | Item | DONE | DONE | DONE | ITMDBCollection | TTMDBCollection | ITMDBCollection = interface; | TTMDBCollection = class; | ITMDBCollection = interface(ITMDBItem) | TTMDBCollection = class(TTMDBItem, ITMDBCollection) | TMDB
Collections | Collections | Items | DONE | DONE | DONE | ITMDBCollections | TTMDBCollections | ITMDBCollections = interface; | TTMDBCollections = class; | ITMDBCollections = interface(ITMDBItems) | TTMDBCollections = class(TTMDBItems, ITMDBCollections) | TMDB
Collections | CollectionPage | Page | DONE | DONE | DONE | ITMDBCollectionPage | TTMDBCollectionPage | ITMDBCollectionPage = interface; | TTMDBCollectionPage = class; | ITMDBCollectionPage = interface(ITMDBPage) | TTMDBCollectionPage = class(TTMDBPage, ITMDBCollectionPage) | TMDB
Collections | CollectionDetail | Detail | DONE | DONE | DONE | ITMDBCollectionDetail | TTMDBCollectionDetail | ITMDBCollectionDetail = interface; | TTMDBCollectionDetail = class; | ITMDBCollectionDetail = interface(ITMDBDetail) | TTMDBCollectionDetail = class(TTMDBDetail, ITMDBCollectionDetail) | TMDB
Discover | DiscoverMoviesParams |  | DONE | DONE | TODO | ITMDBDiscoverMoviesParams | TTMDBDiscoverMoviesParams | ITMDBDiscoverMoviesParams = interface; | TTMDBDiscoverMoviesParams = class; | ITMDBDiscoverMoviesParams = interface | TTMDBDiscoverMoviesParams = class(TInterfacedObject, ITMDBDiscoverMoviesParams) | TMDB
Discover | DiscoverTVParams |  | DONE | DONE | TODO | ITMDBDiscoverTVParams | TTMDBDiscoverTVParams | ITMDBDiscoverTVParams = interface; | TTMDBDiscoverTVParams = class; | ITMDBDiscoverTVParams = interface | TTMDBDiscoverTVParams = class(TInterfacedObject, ITMDBDiscoverTVParams) | TMDB
Find | FindResults |  | DONE | DONE | TODO | ITMDBFindResults | TTMDBFindResults | ITMDBFindResults = interface; | TTMDBFindResults = class; | ITMDBFindResults = interface | TTMDBFindResults = class(TInterfacedObject, ITMDBFindResults) | TMDB
People | Person | Medium | DONE | DONE | TEST | ITMDBPerson | TTMDBPerson | ITMDBPerson = interface; | TTMDBPerson = class; | ITMDBPerson = interface(ITMDBMedium) | TTMDBPerson = class(TTMDBMedium, ITMDBPerson) | TMDB
People | People | Media | DONE | DONE | TEST | ITMDBPeople | TTMDBPeople | ITMDBPeople = interface; | TTMDBPeople = class; | ITMDBPeople = interface(ITMDBMedia) | TTMDBPeople = class(TTMDBMedia, ITMDBPeople) | TMDB
People | PersonPage | MediaPage | DONE | DONE | TEST | ITMDBPersonPage | TTMDBPersonPage | ITMDBPersonPage = interface; | TTMDBPersonPage = class; | ITMDBPersonPage = interface(ITMDBMediaPage) | TTMDBPersonPage = class(TTMDBMediaPage, ITMDBPersonPage) | TMDB
People | PersonDetail | Detail | DONE | DONE | TODO | ITMDBPersonDetail | TTMDBPersonDetail | ITMDBPersonDetail = interface; | TTMDBPersonDetail = class; | ITMDBPersonDetail = interface(ITMDBDetail) | TTMDBPersonDetail = class(TTMDBDetail, ITMDBPersonDetail) | TMDB
Credits | CastPerson | Person | DONE | DONE | DONE | ITMDBCastPerson | TTMDBCastPerson | ITMDBCastPerson = interface; | TTMDBCastPerson = class; | ITMDBCastPerson = interface(ITMDBPerson) | TTMDBCastPerson = class(TTMDBPerson, ITMDBCastPerson) | TMDB
Credits | CastPeople | People | DONE | DONE | DONE | ITMDBCastPeople | TTMDBCastPeople | ITMDBCastPeople = interface; | TTMDBCastPeople = class; | ITMDBCastPeople = interface(ITMDBPeople) | TTMDBCastPeople = class(TTMDBPeople, ITMDBCastPeople) | TMDB
Credits | CrewPerson | Person | DONE | DONE | DONE | ITMDBCrewPerson | TTMDBCrewPerson | ITMDBCrewPerson = interface; | TTMDBCrewPerson = class; | ITMDBCrewPerson = interface(ITMDBPerson) | TTMDBCrewPerson = class(TTMDBPerson, ITMDBCrewPerson) | TMDB
Credits | CrewPeople | People | DONE | DONE | DONE | ITMDBCrewPeople | TTMDBCrewPeople | ITMDBCrewPeople = interface; | TTMDBCrewPeople = class; | ITMDBCrewPeople = interface(ITMDBPeople) | TTMDBCrewPeople = class(TTMDBPeople, ITMDBCrewPeople) | TMDB
Credits | Credits |  | DONE | DONE | DONE | ITMDBCredits | TTMDBCredits | ITMDBCredits = interface; | TTMDBCredits = class; | ITMDBCredits = interface | TTMDBCredits = class(TInterfacedObject, ITMDBCredits) | TMDB
Credits | CreditDetail |  | DONE | DONE | TODO | ITMDBCreditDetail | TTMDBCreditDetail | ITMDBCreditDetail = interface; | TTMDBCreditDetail = class; | ITMDBCreditDetail = interface | TTMDBCreditDetail = class(TInterfacedObject, ITMDBCreditDetail) | TMDB
Credits | CreditRole | Item | DONE | DONE | TODO | ITMDBCreditRole | TTMDBCreditRole | ITMDBCreditRole = interface; | TTMDBCreditRole = class; | ITMDBCreditRole = interface(ITMDBItem) | TTMDBCreditRole = class(TTMDBItem, ITMDBCreditRole) | TMDB
Credits | CreditRoles | Items | DONE | DONE | TODO | ITMDBCreditRoles | TTMDBCreditRoles | ITMDBCreditRoles = interface; | TTMDBCreditRoles = class; | ITMDBCreditRoles = interface(ITMDBItems) | TTMDBCreditRoles = class(TTMDBItems, ITMDBCreditRoles) | TMDB
Credits | CreditJob | Item | DONE | DONE | TODO | ITMDBCreditJob | TTMDBCreditJob | ITMDBCreditJob = interface; | TTMDBCreditJob = class; | ITMDBCreditJob = interface(ITMDBItem) | TTMDBCreditJob = class(TTMDBItem, ITMDBCreditJob) | TMDB
Credits | CreditJobs | Items | DONE | DONE | TODO | ITMDBCreditJobs | TTMDBCreditJobs | ITMDBCreditJobs = interface; | TTMDBCreditJobs = class; | ITMDBCreditJobs = interface(ITMDBItems) | TTMDBCreditJobs = class(TTMDBItems, ITMDBCreditJobs) | TMDB
Credits | AggregateCastPerson | CastPerson | DONE | DONE | TODO | ITMDBAggregateCastPerson | TTMDBAggregateCastPerson | ITMDBAggregateCastPerson = interface; | TTMDBAggregateCastPerson = class; | ITMDBAggregateCastPerson = interface(ITMDBCastPerson) | TTMDBAggregateCastPerson = class(TTMDBCastPerson, ITMDBAggregateCastPerson) | TMDB
Credits | AggregateCastPeople | CastPeople | DONE | DONE | TODO | ITMDBAggregateCastPeople | TTMDBAggregateCastPeople | ITMDBAggregateCastPeople = interface; | TTMDBAggregateCastPeople = class; | ITMDBAggregateCastPeople = interface(ITMDBCastPeople) | TTMDBAggregateCastPeople = class(TTMDBCastPeople, ITMDBAggregateCastPeople) | TMDB
Credits | AggregateCrewPerson | CrewPerson | DONE | DONE | TODO | ITMDBAggregateCrewPerson | TTMDBAggregateCrewPerson | ITMDBAggregateCrewPerson = interface; | TTMDBAggregateCrewPerson = class; | ITMDBAggregateCrewPerson = interface(ITMDBCrewPerson) | TTMDBAggregateCrewPerson = class(TTMDBCrewPerson, ITMDBAggregateCrewPerson) | TMDB
Credits | AggregateCrewPeople | CrewPeople | DONE | DONE | TODO | ITMDBAggregateCrewPeople | TTMDBAggregateCrewPeople | ITMDBAggregateCrewPeople = interface; | TTMDBAggregateCrewPeople = class; | ITMDBAggregateCrewPeople = interface(ITMDBCrewPeople) | TTMDBAggregateCrewPeople = class(TTMDBCrewPeople, ITMDBAggregateCrewPeople) | TMDB
Credits | AggregateCredits |  | DONE | DONE | TODO | ITMDBAggregateCredits | TTMDBAggregateCredits | ITMDBAggregateCredits = interface; | TTMDBAggregateCredits = class; | ITMDBAggregateCredits = interface | TTMDBAggregateCredits = class(TInterfacedObject, ITMDBAggregateCredits) | TMDB
Credits | CombinedCastCredit | Medium | DONE | DONE | TODO | ITMDBCombinedCastCredit | TTMDBCombinedCastCredit | ITMDBCombinedCastCredit = interface; | TTMDBCombinedCastCredit = class; | ITMDBCombinedCastCredit = interface(ITMDBMedium) | TTMDBCombinedCastCredit = class(TTMDBMedium, ITMDBCombinedCastCredit) | TMDB
Credits | CombinedCastCredits | Media | DONE | DONE | TODO | ITMDBCombinedCastCredits | TTMDBCombinedCastCredits | ITMDBCombinedCastCredits = interface; | TTMDBCombinedCastCredits = class; | ITMDBCombinedCastCredits = interface(ITMDBMedia) | TTMDBCombinedCastCredits = class(TTMDBMedia, ITMDBCombinedCastCredits) | TMDB
Credits | CombinedCrewCredit | Medium | DONE | DONE | TODO | ITMDBCombinedCrewCredit | TTMDBCombinedCrewCredit | ITMDBCombinedCrewCredit = interface; | TTMDBCombinedCrewCredit = class; | ITMDBCombinedCrewCredit = interface(ITMDBMedium) | TTMDBCombinedCrewCredit = class(TTMDBMedium, ITMDBCombinedCrewCredit) | TMDB
Credits | CombinedCrewCredits | Media | DONE | DONE | TODO | ITMDBCombinedCrewCredits | TTMDBCombinedCrewCredits | ITMDBCombinedCrewCredits = interface; | TTMDBCombinedCrewCredits = class; | ITMDBCombinedCrewCredits = interface(ITMDBMedia) | TTMDBCombinedCrewCredits = class(TTMDBMedia, ITMDBCombinedCrewCredits) | TMDB
Credits | CombinedCredits |  | DONE | DONE | TODO | ITMDBCombinedCredits | TTMDBCombinedCredits | ITMDBCombinedCredits = interface; | TTMDBCombinedCredits = class; | ITMDBCombinedCredits = interface | TTMDBCombinedCredits = class(TInterfacedObject, ITMDBCombinedCredits) | TMDB
Lists | List | Item | DONE | DONE | TODO | ITMDBList | TTMDBList | ITMDBList = interface; | TTMDBList = class; | ITMDBList = interface(ITMDBItem) | TTMDBList = class(TTMDBItem, ITMDBList) | TMDB
Lists | Lists | Items | DONE | DONE | TODO | ITMDBLists | TTMDBLists | ITMDBLists = interface; | TTMDBLists = class; | ITMDBLists = interface(ITMDBItems) | TTMDBLists = class(TTMDBItems, ITMDBLists) | TMDB
Lists | ListPage | Page | DONE | DONE | TODO | ITMDBListPage | TTMDBListPage | ITMDBListPage = interface; | TTMDBListPage = class; | ITMDBListPage = interface(ITMDBPage) | TTMDBListPage = class(TTMDBPage, ITMDBListPage) | TMDB
Lists | ListDetail | Detail | DONE | DONE | TODO | ITMDBListDetail | TTMDBListDetail | ITMDBListDetail = interface; | TTMDBListDetail = class; | ITMDBListDetail = interface(ITMDBDetail) | TTMDBListDetail = class(TTMDBDetail, ITMDBListDetail) | TMDB
Reviews | ReviewAuthor |  | DONE | DONE | TEST | ITMDBReviewAuthor | TTMDBReviewAuthor | ITMDBReviewAuthor = interface; | TTMDBReviewAuthor = class; | ITMDBReviewAuthor = interface | TTMDBReviewAuthor = class(TInterfacedObject, ITMDBReviewAuthor) | TMDB
Reviews | Review | Item | DONE | DONE | TEST | ITMDBReview | TTMDBReview | ITMDBReview = interface; | TTMDBReview = class; | ITMDBReview = interface(ITMDBItem) | TTMDBReview = class(TTMDBItem, ITMDBReview) | TMDB
Reviews | Reviews | Items | DONE | DONE | TEST | ITMDBReviews | TTMDBReviews | ITMDBReviews = interface; | TTMDBReviews = class; | ITMDBReviews = interface(ITMDBItems) | TTMDBReviews = class(TTMDBItems, ITMDBReviews) | TMDB
Reviews | ReviewPage | Page | DONE | DONE | TEST | ITMDBReviewPage | TTMDBReviewPage | ITMDBReviewPage = interface; | TTMDBReviewPage = class; | ITMDBReviewPage = interface(ITMDBPage) | TTMDBReviewPage = class(TTMDBPage, ITMDBReviewPage) | TMDB
Reviews | ReviewDetail |  | DONE | DONE | TODO | ITMDBReviewDetail | TTMDBReviewDetail | ITMDBReviewDetail = interface; | TTMDBReviewDetail = class; | ITMDBReviewDetail = interface | TTMDBReviewDetail = class(TInterfacedObject, ITMDBReviewDetail) | TMDB
Movies | Movie | Medium | DONE | DONE | DONE | ITMDBMovie | TTMDBMovie | ITMDBMovie = interface; | TTMDBMovie = class; | ITMDBMovie = interface(ITMDBMedium) | TTMDBMovie = class(TTMDBMedium, ITMDBMovie) | TMDB
Movies | Movies | Media | DONE | DONE | DONE | ITMDBMovies | TTMDBMovies | ITMDBMovies = interface; | TTMDBMovies = class; | ITMDBMovies = interface(ITMDBMedia) | TTMDBMovies = class(TTMDBMedia, ITMDBMovies) | TMDB
Movies | MoviePage | MediaPage | DONE | DONE | DONE | ITMDBMoviePage | TTMDBMoviePage | ITMDBMoviePage = interface; | TTMDBMoviePage = class; | ITMDBMoviePage = interface(ITMDBMediaPage) | TTMDBMoviePage = class(TTMDBMediaPage, ITMDBMoviePage) | TMDB
Movies | RatedMovie | Movie | DONE | DONE | TODO | ITMDBRatedMovie | TTMDBRatedMovie | ITMDBRatedMovie = interface; | TTMDBRatedMovie = class; | ITMDBRatedMovie = interface(ITMDBMovie) | TTMDBRatedMovie = class(TTMDBMovie, ITMDBRatedMovie) | TMDB
Movies | RatedMovies | Movies | DONE | DONE | TODO | ITMDBRatedMovies | TTMDBRatedMovies | ITMDBRatedMovies = interface; | TTMDBRatedMovies = class; | ITMDBRatedMovies = interface(ITMDBMovies) | TTMDBRatedMovies = class(TTMDBMovies, ITMDBRatedMovies) | TMDB
Movies | RatedMoviePage | MoviePage | DONE | DONE | TODO | ITMDBRatedMoviePage | TTMDBRatedMoviePage | ITMDBRatedMoviePage = interface; | TTMDBRatedMoviePage = class; | ITMDBRatedMoviePage = interface(ITMDBMoviePage) | TTMDBRatedMoviePage = class(TTMDBMoviePage, ITMDBRatedMoviePage) | TMDB
Movies | MovieCollectionRef |  | DONE | DONE | TODO | ITMDBMovieCollectionRef | TTMDBMovieCollectionRef | ITMDBMovieCollectionRef = interface; | TTMDBMovieCollectionRef = class; | ITMDBMovieCollectionRef = interface | TTMDBMovieCollectionRef = class(TInterfacedObject, ITMDBMovieCollectionRef) | TMDB
Movies | MovieDetail | Detail | DONE | DONE | IN PROGRESS | ITMDBMovieDetail | TTMDBMovieDetail | ITMDBMovieDetail = interface; | TTMDBMovieDetail = class; | ITMDBMovieDetail = interface(ITMDBDetail) | TTMDBMovieDetail = class(TTMDBDetail, ITMDBMovieDetail) | TMDB
Movie Lists | DateRange |  | DONE | DONE | TODO | ITMDBDateRange | TTMDBDateRange | ITMDBDateRange = interface; | TTMDBDateRange = class; | ITMDBDateRange = interface | TTMDBDateRange = class(TInterfacedObject, ITMDBDateRange) | TMDB
Movie Lists | DatedMoviePage | MoviePage | DONE | DONE | TODO | ITMDBDatedMoviePage | TTMDBDatedMoviePage | ITMDBDatedMoviePage = interface; | TTMDBDatedMoviePage = class; | ITMDBDatedMoviePage = interface(ITMDBMoviePage) | TTMDBDatedMoviePage = class(TTMDBMoviePage, ITMDBDatedMoviePage) | TMDB
TV Series | TVSerie | Medium | IN PROGRESS | IN PROGRESS | IN PROGRESS | ITMDBTVSerie | TTMDBTVSerie | ITMDBTVSerie = interface; | TTMDBTVSerie = class; | ITMDBTVSerie = interface(ITMDBMedium) | TTMDBTVSerie = class(TTMDBMedium, ITMDBTVSerie) | TMDB
TV Series | TVSeries | Media | DONE | DONE | DONE | ITMDBTVSeries | TTMDBTVSeries | ITMDBTVSeries = interface; | TTMDBTVSeries = class; | ITMDBTVSeries = interface(ITMDBMedia) | TTMDBTVSeries = class(TTMDBMedia, ITMDBTVSeries) | TMDB
TV Series | TVSeriesPage | MediaPage | DONE | DONE | DONE | ITMDBTVSeriesPage | TTMDBTVSeriesPage | ITMDBTVSeriesPage = interface; | TTMDBTVSeriesPage = class; | ITMDBTVSeriesPage = interface(ITMDBMediaPage) | TTMDBTVSeriesPage = class(TTMDBMediaPage, ITMDBTVSeriesPage) | TMDB
TV Series | RatedTVSerie | TVSerie | DONE | DONE | TODO | ITMDBRatedTVSerie | TTMDBRatedTVSerie | ITMDBRatedTVSerie = interface; | TTMDBRatedTVSerie = class; | ITMDBRatedTVSerie = interface(ITMDBTVSerie) | TTMDBRatedTVSerie = class(TTMDBTVSerie, ITMDBRatedTVSerie) | TMDB
TV Series | RatedTVSeries | TVSeries | DONE | DONE | TODO | ITMDBRatedTVSeries | TTMDBRatedTVSeries | ITMDBRatedTVSeries = interface; | TTMDBRatedTVSeries = class; | ITMDBRatedTVSeries = interface(ITMDBTVSeries) | TTMDBRatedTVSeries = class(TTMDBTVSeries, ITMDBRatedTVSeries) | TMDB
TV Series | RatedTVSeriesPage | TVSeriesPage | DONE | DONE | TODO | ITMDBRatedTVSeriesPage | TTMDBRatedTVSeriesPage | ITMDBRatedTVSeriesPage = interface; | TTMDBRatedTVSeriesPage = class; | ITMDBRatedTVSeriesPage = interface(ITMDBTVSeriesPage) | TTMDBRatedTVSeriesPage = class(TTMDBTVSeriesPage, ITMDBRatedTVSeriesPage) | TMDB
TV Series | TVSerieDetail | Detail | IN PROGRESS | IN PROGRESS | IN PROGRESS | ITMDBTVSerieDetail | TTMDBTVSerieDetail | ITMDBTVSerieDetail = interface; | TTMDBTVSerieDetail = class; | ITMDBTVSerieDetail = interface(ITMDBDetail) | TTMDBTVSerieDetail = class(TTMDBDetail, ITMDBTVSerieDetail) | TMDB
Screened Theatrically | ScreenedTheatricallyRef | Item | DONE | DONE | TODO | ITMDBScreenedTheatricallyRef | TTMDBScreenedTheatricallyRef | ITMDBScreenedTheatricallyRef = interface; | TTMDBScreenedTheatricallyRef = class; | ITMDBScreenedTheatricallyRef = interface(ITMDBItem) | TTMDBScreenedTheatricallyRef = class(TTMDBItem, ITMDBScreenedTheatricallyRef) | TMDB
Screened Theatrically | ScreenedTheatrically | Items | DONE | DONE | TODO | ITMDBScreenedTheatrically | TTMDBScreenedTheatrically | ITMDBScreenedTheatrically = interface; | TTMDBScreenedTheatrically = class; | ITMDBScreenedTheatrically = interface(ITMDBItems) | TTMDBScreenedTheatrically = class(TTMDBItems, ITMDBScreenedTheatrically) | TMDB
TV Seasons | TVSeason | Medium | DONE | DONE | TODO | ITMDBTVSeason | TTMDBTVSeason | ITMDBTVSeason = interface; | TTMDBTVSeason = class; | ITMDBTVSeason = interface(ITMDBMedium) | TTMDBTVSeason = class(TTMDBMedium, ITMDBTVSeason) | TMDB
TV Seasons | TVSeasons | Media | DONE | DONE | TODO | ITMDBTVSeasons | TTMDBTVSeasons | ITMDBTVSeasons = interface; | TTMDBTVSeasons = class; | ITMDBTVSeasons = interface(ITMDBMedia) | TTMDBTVSeasons = class(TTMDBMedia, ITMDBTVSeasons) | TMDB
TV Seasons | TVSeasonPage | MediaPage | DONE | DONE | TODO | ITMDBTVSeasonPage | TTMDBTVSeasonPage | ITMDBTVSeasonPage = interface; | TTMDBTVSeasonPage = class; | ITMDBTVSeasonPage = interface(ITMDBMediaPage) | TTMDBTVSeasonPage = class(TTMDBMediaPage, ITMDBTVSeasonPage) | TMDB
TV Seasons | TVSeasonDetail | Detail | DONE | DONE | TODO | ITMDBTVSeasonDetail | TTMDBTVSeasonDetail | ITMDBTVSeasonDetail = interface; | TTMDBTVSeasonDetail = class; | ITMDBTVSeasonDetail = interface(ITMDBDetail) | TTMDBTVSeasonDetail = class(TTMDBDetail, ITMDBTVSeasonDetail) | TMDB
TV Seasons | TVSeasonEpisode | TVEpisode | DONE | DONE | TODO | ITMDBTVSeasonEpisode | TTMDBTVSeasonEpisode | ITMDBTVSeasonEpisode = interface; | TTMDBTVSeasonEpisode = class; | ITMDBTVSeasonEpisode = interface(ITMDBTVEpisode) | TTMDBTVSeasonEpisode = class(TTMDBTVEpisode, ITMDBTVSeasonEpisode) | TMDB
TV Seasons | TVSeasonEpisodes | TVEpisodes | DONE | DONE | TODO | ITMDBTVSeasonEpisodes | TTMDBTVSeasonEpisodes | ITMDBTVSeasonEpisodes = interface; | TTMDBTVSeasonEpisodes = class; | ITMDBTVSeasonEpisodes = interface(ITMDBTVEpisodes) | TTMDBTVSeasonEpisodes = class(TTMDBTVEpisodes, ITMDBTVSeasonEpisodes) | TMDB
TV Episodes | TVEpisode | Medium | DONE | DONE | TODO | ITMDBTVEpisode | TTMDBTVEpisode | ITMDBTVEpisode = interface; | TTMDBTVEpisode = class; | ITMDBTVEpisode = interface(ITMDBMedium) | TTMDBTVEpisode = class(TTMDBMedium, ITMDBTVEpisode) | TMDB
TV Episodes | TVEpisodes | Media | DONE | DONE | TODO | ITMDBTVEpisodes | TTMDBTVEpisodes | ITMDBTVEpisodes = interface; | TTMDBTVEpisodes = class; | ITMDBTVEpisodes = interface(ITMDBMedia) | TTMDBTVEpisodes = class(TTMDBMedia, ITMDBTVEpisodes) | TMDB
TV Episodes | TVEpisodePage | MediaPage | DONE | DONE | TODO | ITMDBTVEpisodePage | TTMDBTVEpisodePage | ITMDBTVEpisodePage = interface; | TTMDBTVEpisodePage = class; | ITMDBTVEpisodePage = interface(ITMDBMediaPage) | TTMDBTVEpisodePage = class(TTMDBMediaPage, ITMDBTVEpisodePage) | TMDB
TV Episodes | RatedTVEpisode | TVEpisode | DONE | DONE | TODO | ITMDBRatedTVEpisode | TTMDBRatedTVEpisode | ITMDBRatedTVEpisode = interface; | TTMDBRatedTVEpisode = class; | ITMDBRatedTVEpisode = interface(ITMDBTVEpisode) | TTMDBRatedTVEpisode = class(TTMDBTVEpisode, ITMDBRatedTVEpisode) | TMDB
TV Episodes | RatedTVEpisodes | TVEpisodes | DONE | DONE | TODO | ITMDBRatedTVEpisodes | TTMDBRatedTVEpisodes | ITMDBRatedTVEpisodes = interface; | TTMDBRatedTVEpisodes = class; | ITMDBRatedTVEpisodes = interface(ITMDBTVEpisodes) | TTMDBRatedTVEpisodes = class(TTMDBTVEpisodes, ITMDBRatedTVEpisodes) | TMDB
TV Episodes | TVEpisodeDetail | Detail | DONE | DONE | TODO | ITMDBTVEpisodeDetail | TTMDBTVEpisodeDetail | ITMDBTVEpisodeDetail = interface; | TTMDBTVEpisodeDetail = class; | ITMDBTVEpisodeDetail = interface(ITMDBDetail) | TTMDBTVEpisodeDetail = class(TTMDBDetail, ITMDBTVEpisodeDetail) | TMDB
TV Episode Groups | TVEpisodeGroup |  | DONE | DONE | TODO | ITMDBTVEpisodeGroup | TTMDBTVEpisodeGroup | ITMDBTVEpisodeGroup = interface; | TTMDBTVEpisodeGroup = class; | ITMDBTVEpisodeGroup = interface | TTMDBTVEpisodeGroup = class(TInterfacedObject, ITMDBTVEpisodeGroup) | TMDB
TV Episode Groups | TVEpisodeGroups |  | DONE | DONE | TODO | ITMDBTVEpisodeGroups | TTMDBTVEpisodeGroups | ITMDBTVEpisodeGroups = interface; | TTMDBTVEpisodeGroups = class; | ITMDBTVEpisodeGroups = interface | TTMDBTVEpisodeGroups = class(TInterfacedObject, ITMDBTVEpisodeGroups) | TMDB
Watch Providers | WatchProviderPriority |  | DONE | DONE | TODO | ITMDBWatchProviderPriority | TTMDBWatchProviderPriority | ITMDBWatchProviderPriority = interface; | TTMDBWatchProviderPriority = class; | ITMDBWatchProviderPriority = interface | TTMDBWatchProviderPriority = class(TInterfacedObject, ITMDBWatchProviderPriority) | TMDB
Watch Providers | WatchProviderPriorities |  | DONE | DONE | TODO | ITMDBWatchProviderPriorities | TTMDBWatchProviderPriorities | ITMDBWatchProviderPriorities = interface; | TTMDBWatchProviderPriorities = class; | ITMDBWatchProviderPriorities = interface | TTMDBWatchProviderPriorities = class(TInterfacedObject, ITMDBWatchProviderPriorities) | TMDB
Watch Providers | WatchProvider | Item | DONE | DONE | TODO | ITMDBWatchProvider | TTMDBWatchProvider | ITMDBWatchProvider = interface; | TTMDBWatchProvider = class; | ITMDBWatchProvider = interface(ITMDBItem) | TTMDBWatchProvider = class(TTMDBItem, ITMDBWatchProvider) | TMDB
Watch Providers | WatchProviders | Items | DONE | DONE | TODO | ITMDBWatchProviders | TTMDBWatchProviders | ITMDBWatchProviders = interface; | TTMDBWatchProviders = class; | ITMDBWatchProviders = interface(ITMDBItems) | TTMDBWatchProviders = class(TTMDBItems, ITMDBWatchProviders) | TMDB
Watch Providers | MediaWatchProvider | Item | TODO | TODO | TODO | ITMDBMediaWatchProvider | TTMDBMediaWatchProvider | ITMDBMediaWatchProvider = interface; | TTMDBMediaWatchProvider = class; | ITMDBMediaWatchProvider = interface(ITMDBItem) | TTMDBMediaWatchProvider = class(TTMDBItem, ITMDBMediaWatchProvider) | TMDB
Watch Providers | MediaWatchProviders | Items | TODO | TODO | TODO | ITMDBMediaWatchProviders | TTMDBMediaWatchProviders | ITMDBMediaWatchProviders = interface; | TTMDBMediaWatchProviders = class; | ITMDBMediaWatchProviders = interface(ITMDBItems) | TTMDBMediaWatchProviders = class(TTMDBItems, ITMDBMediaWatchProviders) | TMDB
API Namespaces | Namespace |  | DONE | DONE | DONE | ITMDBNamespace | TTMDBNamespace | ITMDBNamespace = interface; | TTMDBNamespace = class; | ITMDBNamespace = interface | TTMDBNamespace = class(TInterfacedObject, ITMDBNamespace) | TMDB
API Namespaces | NamespaceAccount | ITMDBNamespace | DONE | DONE | TEST | ITMDBNamespaceAccount | TTMDBNamespaceAccount | ITMDBNamespaceAccount = interface; | TTMDBNamespaceAccount = class; | ITMDBNamespaceAccount = interface(ITMDBITMDBNamespace) | TTMDBNamespaceAccount = class(TTMDBITMDBNamespace, ITMDBNamespaceAccount) | TMDB
API Namespaces | NamespaceAuthentication | ITMDBNamespace | DONE | DONE | TEST | ITMDBNamespaceAuthentication | TTMDBNamespaceAuthentication | ITMDBNamespaceAuthentication = interface; | TTMDBNamespaceAuthentication = class; | ITMDBNamespaceAuthentication = interface(ITMDBITMDBNamespace) | TTMDBNamespaceAuthentication = class(TTMDBITMDBNamespace, ITMDBNamespaceAuthentication) | TMDB
API Namespaces | NamespaceCertifications | ITMDBNamespace | DONE | DONE | DONE | ITMDBNamespaceCertifications | TTMDBNamespaceCertifications | ITMDBNamespaceCertifications = interface; | TTMDBNamespaceCertifications = class; | ITMDBNamespaceCertifications = interface(ITMDBITMDBNamespace) | TTMDBNamespaceCertifications = class(TTMDBITMDBNamespace, ITMDBNamespaceCertifications) | TMDB
API Namespaces | NamespaceChanges | ITMDBNamespace | DONE | DONE | TODO | ITMDBNamespaceChanges | TTMDBNamespaceChanges | ITMDBNamespaceChanges = interface; | TTMDBNamespaceChanges = class; | ITMDBNamespaceChanges = interface(ITMDBITMDBNamespace) | TTMDBNamespaceChanges = class(TTMDBITMDBNamespace, ITMDBNamespaceChanges) | TMDB
API Namespaces | NamespaceCollections | ITMDBNamespace | DONE | DONE | TEST | ITMDBNamespaceCollections | TTMDBNamespaceCollections | ITMDBNamespaceCollections = interface; | TTMDBNamespaceCollections = class; | ITMDBNamespaceCollections = interface(ITMDBITMDBNamespace) | TTMDBNamespaceCollections = class(TTMDBITMDBNamespace, ITMDBNamespaceCollections) | TMDB
API Namespaces | NamespaceCompanies | ITMDBNamespace | DONE | DONE | TEST | ITMDBNamespaceCompanies | TTMDBNamespaceCompanies | ITMDBNamespaceCompanies = interface; | TTMDBNamespaceCompanies = class; | ITMDBNamespaceCompanies = interface(ITMDBITMDBNamespace) | TTMDBNamespaceCompanies = class(TTMDBITMDBNamespace, ITMDBNamespaceCompanies) | TMDB
API Namespaces | NamespaceConfiguration | ITMDBNamespace | DONE | DONE | IN PROGRESS | ITMDBNamespaceConfiguration | TTMDBNamespaceConfiguration | ITMDBNamespaceConfiguration = interface; | TTMDBNamespaceConfiguration = class; | ITMDBNamespaceConfiguration = interface(ITMDBITMDBNamespace) | TTMDBNamespaceConfiguration = class(TTMDBITMDBNamespace, ITMDBNamespaceConfiguration) | TMDB
API Namespaces | NamespaceCredits | ITMDBNamespace | DONE | DONE | TODO | ITMDBNamespaceCredits | TTMDBNamespaceCredits | ITMDBNamespaceCredits = interface; | TTMDBNamespaceCredits = class; | ITMDBNamespaceCredits = interface(ITMDBITMDBNamespace) | TTMDBNamespaceCredits = class(TTMDBITMDBNamespace, ITMDBNamespaceCredits) | TMDB
API Namespaces | NamespaceDiscover | ITMDBNamespace | DONE | DONE | TODO | ITMDBNamespaceDiscover | TTMDBNamespaceDiscover | ITMDBNamespaceDiscover = interface; | TTMDBNamespaceDiscover = class; | ITMDBNamespaceDiscover = interface(ITMDBITMDBNamespace) | TTMDBNamespaceDiscover = class(TTMDBITMDBNamespace, ITMDBNamespaceDiscover) | TMDB
API Namespaces | NamespaceFind | ITMDBNamespace | DONE | DONE | TODO | ITMDBNamespaceFind | TTMDBNamespaceFind | ITMDBNamespaceFind = interface; | TTMDBNamespaceFind = class; | ITMDBNamespaceFind = interface(ITMDBITMDBNamespace) | TTMDBNamespaceFind = class(TTMDBITMDBNamespace, ITMDBNamespaceFind) | TMDB
API Namespaces | NamespaceGenres | ITMDBNamespace | DONE | DONE | DONE | ITMDBNamespaceGenres | TTMDBNamespaceGenres | ITMDBNamespaceGenres = interface; | TTMDBNamespaceGenres = class; | ITMDBNamespaceGenres = interface(ITMDBITMDBNamespace) | TTMDBNamespaceGenres = class(TTMDBITMDBNamespace, ITMDBNamespaceGenres) | TMDB
API Namespaces | NamespaceGuestSessions | ITMDBNamespace | DONE | DONE | TODO | ITMDBNamespaceGuestSessions | TTMDBNamespaceGuestSessions | ITMDBNamespaceGuestSessions = interface; | TTMDBNamespaceGuestSessions = class; | ITMDBNamespaceGuestSessions = interface(ITMDBITMDBNamespace) | TTMDBNamespaceGuestSessions = class(TTMDBITMDBNamespace, ITMDBNamespaceGuestSessions) | TMDB
API Namespaces | NamespaceKeywords | ITMDBNamespace | DONE | DONE | DONE | ITMDBNamespaceKeywords | TTMDBNamespaceKeywords | ITMDBNamespaceKeywords = interface; | TTMDBNamespaceKeywords = class; | ITMDBNamespaceKeywords = interface(ITMDBITMDBNamespace) | TTMDBNamespaceKeywords = class(TTMDBITMDBNamespace, ITMDBNamespaceKeywords) | TMDB
API Namespaces | NamespaceLists | ITMDBNamespace | TODO | TODO | TODO | ITMDBNamespaceLists | TTMDBNamespaceLists | ITMDBNamespaceLists = interface; | TTMDBNamespaceLists = class; | ITMDBNamespaceLists = interface(ITMDBITMDBNamespace) | TTMDBNamespaceLists = class(TTMDBITMDBNamespace, ITMDBNamespaceLists) | TMDB
API Namespaces | NamespaceMovieLists | ITMDBNamespace | DONE | DONE | TODO | ITMDBNamespaceMovieLists | TTMDBNamespaceMovieLists | ITMDBNamespaceMovieLists = interface; | TTMDBNamespaceMovieLists = class; | ITMDBNamespaceMovieLists = interface(ITMDBITMDBNamespace) | TTMDBNamespaceMovieLists = class(TTMDBITMDBNamespace, ITMDBNamespaceMovieLists) | TMDB
API Namespaces | NamespaceMovies | ITMDBNamespace | IN PROGRESS | IN PROGRESS | IN PROGRESS | ITMDBNamespaceMovies | TTMDBNamespaceMovies | ITMDBNamespaceMovies = interface; | TTMDBNamespaceMovies = class; | ITMDBNamespaceMovies = interface(ITMDBITMDBNamespace) | TTMDBNamespaceMovies = class(TTMDBITMDBNamespace, ITMDBNamespaceMovies) | TMDB
API Namespaces | NamespaceNetworks | ITMDBNamespace | DONE | DONE | IN PROGRESS | ITMDBNamespaceNetworks | TTMDBNamespaceNetworks | ITMDBNamespaceNetworks = interface; | TTMDBNamespaceNetworks = class; | ITMDBNamespaceNetworks = interface(ITMDBITMDBNamespace) | TTMDBNamespaceNetworks = class(TTMDBITMDBNamespace, ITMDBNamespaceNetworks) | TMDB
API Namespaces | NamespacePeopleLists | ITMDBNamespace | DONE | DONE | TODO | ITMDBNamespacePeopleLists | TTMDBNamespacePeopleLists | ITMDBNamespacePeopleLists = interface; | TTMDBNamespacePeopleLists = class; | ITMDBNamespacePeopleLists = interface(ITMDBITMDBNamespace) | TTMDBNamespacePeopleLists = class(TTMDBITMDBNamespace, ITMDBNamespacePeopleLists) | TMDB
API Namespaces | NamespacePeople | ITMDBNamespace | IN PROGRESS | IN PROGRESS | IN PROGRESS | ITMDBNamespacePeople | TTMDBNamespacePeople | ITMDBNamespacePeople = interface; | TTMDBNamespacePeople = class; | ITMDBNamespacePeople = interface(ITMDBITMDBNamespace) | TTMDBNamespacePeople = class(TTMDBITMDBNamespace, ITMDBNamespacePeople) | TMDB
API Namespaces | NamespaceReviews | ITMDBNamespace | DONE | DONE | TODO | ITMDBNamespaceReviews | TTMDBNamespaceReviews | ITMDBNamespaceReviews = interface; | TTMDBNamespaceReviews = class; | ITMDBNamespaceReviews = interface(ITMDBITMDBNamespace) | TTMDBNamespaceReviews = class(TTMDBITMDBNamespace, ITMDBNamespaceReviews) | TMDB
API Namespaces | NamespaceSearch | ITMDBNamespace | DONE | DONE | TEST | ITMDBNamespaceSearch | TTMDBNamespaceSearch | ITMDBNamespaceSearch = interface; | TTMDBNamespaceSearch = class; | ITMDBNamespaceSearch = interface(ITMDBITMDBNamespace) | TTMDBNamespaceSearch = class(TTMDBITMDBNamespace, ITMDBNamespaceSearch) | TMDB
API Namespaces | NamespaceTrending | ITMDBNamespace | DONE | DONE | TODO | ITMDBNamespaceTrending | TTMDBNamespaceTrending | ITMDBNamespaceTrending = interface; | TTMDBNamespaceTrending = class; | ITMDBNamespaceTrending = interface(ITMDBITMDBNamespace) | TTMDBNamespaceTrending = class(TTMDBITMDBNamespace, ITMDBNamespaceTrending) | TMDB
API Namespaces | NamespaceTVSeriesLists | ITMDBNamespace | DONE | DONE | TODO | ITMDBNamespaceTVSeriesLists | TTMDBNamespaceTVSeriesLists | ITMDBNamespaceTVSeriesLists = interface; | TTMDBNamespaceTVSeriesLists = class; | ITMDBNamespaceTVSeriesLists = interface(ITMDBITMDBNamespace) | TTMDBNamespaceTVSeriesLists = class(TTMDBITMDBNamespace, ITMDBNamespaceTVSeriesLists) | TMDB
API Namespaces | NamespaceTVSeries | ITMDBNamespace | IN PROGRESS | IN PROGRESS | IN PROGRESS | ITMDBNamespaceTVSeries | TTMDBNamespaceTVSeries | ITMDBNamespaceTVSeries = interface; | TTMDBNamespaceTVSeries = class; | ITMDBNamespaceTVSeries = interface(ITMDBITMDBNamespace) | TTMDBNamespaceTVSeries = class(TTMDBITMDBNamespace, ITMDBNamespaceTVSeries) | TMDB
API Namespaces | NamespaceTVSeasons | ITMDBNamespace | IN PROGRESS | IN PROGRESS | TODO | ITMDBNamespaceTVSeasons | TTMDBNamespaceTVSeasons | ITMDBNamespaceTVSeasons = interface; | TTMDBNamespaceTVSeasons = class; | ITMDBNamespaceTVSeasons = interface(ITMDBITMDBNamespace) | TTMDBNamespaceTVSeasons = class(TTMDBITMDBNamespace, ITMDBNamespaceTVSeasons) | TMDB
API Namespaces | NamespaceTVEpisodes | ITMDBNamespace | IN PROGRESS | IN PROGRESS | TODO | ITMDBNamespaceTVEpisodes | TTMDBNamespaceTVEpisodes | ITMDBNamespaceTVEpisodes = interface; | TTMDBNamespaceTVEpisodes = class; | ITMDBNamespaceTVEpisodes = interface(ITMDBITMDBNamespace) | TTMDBNamespaceTVEpisodes = class(TTMDBITMDBNamespace, ITMDBNamespaceTVEpisodes) | TMDB
API Namespaces | NamespaceTVEpisodeGroups | ITMDBNamespace | DONE | DONE | TODO | ITMDBNamespaceTVEpisodeGroups | TTMDBNamespaceTVEpisodeGroups | ITMDBNamespaceTVEpisodeGroups = interface; | TTMDBNamespaceTVEpisodeGroups = class; | ITMDBNamespaceTVEpisodeGroups = interface(ITMDBITMDBNamespace) | TTMDBNamespaceTVEpisodeGroups = class(TTMDBITMDBNamespace, ITMDBNamespaceTVEpisodeGroups) | TMDB
API Namespaces | NamespaceWatchProviders | ITMDBNamespace | DONE | DONE | TODO | ITMDBNamespaceWatchProviders | TTMDBNamespaceWatchProviders | ITMDBNamespaceWatchProviders = interface; | TTMDBNamespaceWatchProviders = class; | ITMDBNamespaceWatchProviders = interface(ITMDBITMDBNamespace) | TTMDBNamespaceWatchProviders = class(TTMDBITMDBNamespace, ITMDBNamespaceWatchProviders) | TMDB
API Client | Cache |  | DONE | DONE | TEST | ITMDBCache | TTMDBCache | ITMDBCache = interface; | TTMDBCache = class; | ITMDBCache = interface | TTMDBCache = class(TInterfacedObject, ITMDBCache) | TMDB
API Client | LoginState |  | DONE | DONE | TEST | ITMDBLoginState | TTMDBLoginState | ITMDBLoginState = interface; | TTMDBLoginState = class; | ITMDBLoginState = interface | TTMDBLoginState = class(TInterfacedObject, ITMDBLoginState) | TMDB
API Client | Client |  | DONE | DONE | TEST | ITMDBClient | TTMDBClient | ITMDBClient = interface; | TTMDBClient = class; | ITMDBClient = interface | TTMDBClient = class(TInterfacedObject, ITMDBClient) | TMDB
[6 empty] | ITMDB | TTMDB | ITMDB = interface; | TTMDB = class; | ITMDB = interface | TTMDB = class(TInterfacedObject, ITMDB) | TMDB
[6 empty] | ITMDB | TTMDB | ITMDB = interface; | TTMDB = class; | ITMDB = interface | TTMDB = class(TInterfacedObject, ITMDB) | TMDB

## Append to Response
Category | Interfaced Object | Name | Result Type | Status | Function Name | Interface Signature | Implementation Signature
Movies | TTMDBMovieDetail | AccountStates | ITMDBAccountStates | DONE | AppendedAccountStates | function AppendedAccountStates: ITMDBAccountStates; stdcall; | function TTTMDBMovieDetail.AppendedAccountStates: ITMDBAccountStates;
Movies | TTMDBMovieDetail | AlternativeTitles | ITMDBAlternativeTitles | DONE | AppendedAlternativeTitles | function AppendedAlternativeTitles: ITMDBAlternativeTitles; stdcall; | function TTTMDBMovieDetail.AppendedAlternativeTitles: ITMDBAlternativeTitles;
Movies | TTMDBMovieDetail | Changes | ITMDBChanges | TEST | AppendedChanges | function AppendedChanges: ITMDBChanges; stdcall; | function TTTMDBMovieDetail.AppendedChanges: ITMDBChanges;
Movies | TTMDBMovieDetail | Credits | ITMDBCredits | DONE | AppendedCredits | function AppendedCredits: ITMDBCredits; stdcall; | function TTTMDBMovieDetail.AppendedCredits: ITMDBCredits;
Movies | TTMDBMovieDetail | ExternalIDs | ITMDBExternalIDs | DONE | AppendedExternalIDs | function AppendedExternalIDs: ITMDBExternalIDs; stdcall; | function TTTMDBMovieDetail.AppendedExternalIDs: ITMDBExternalIDs;
Movies | TTMDBMovieDetail | Images | ITMDBMediaImageGroup | DONE | AppendedImages | function AppendedImages: ITMDBMediaImageGroup; stdcall; | function TTTMDBMovieDetail.AppendedImages: ITMDBMediaImageGroup;
Movies | TTMDBMovieDetail | Keywords | ITMDBKeywords | DONE | AppendedKeywords | function AppendedKeywords: ITMDBKeywords; stdcall; | function TTTMDBMovieDetail.AppendedKeywords: ITMDBKeywords;
Movies | TTMDBMovieDetail | Lists | ITMDBListPage | TEST | AppendedLists | function AppendedLists: ITMDBListPage; stdcall; | function TTTMDBMovieDetail.AppendedLists: ITMDBListPage;
Movies | TTMDBMovieDetail | Recommendations | ITMDBMediaPage | TEST | AppendedRecommendations | function AppendedRecommendations: ITMDBMediaPage; stdcall; | function TTTMDBMovieDetail.AppendedRecommendations: ITMDBMediaPage;
Movies | TTMDBMovieDetail | ReleaseDates | ITMDBReleaseDates | DONE | AppendedReleaseDates | function AppendedReleaseDates: ITMDBReleaseDates; stdcall; | function TTTMDBMovieDetail.AppendedReleaseDates: ITMDBReleaseDates;
Movies | TTMDBMovieDetail | Reviews | ITMDBReviewPage | DONE | AppendedReviews | function AppendedReviews: ITMDBReviewPage; stdcall; | function TTTMDBMovieDetail.AppendedReviews: ITMDBReviewPage;
Movies | TTMDBMovieDetail | Similar | ITMDBMoviePage | TEST | AppendedSimilar | function AppendedSimilar: ITMDBMoviePage; stdcall; | function TTTMDBMovieDetail.AppendedSimilar: ITMDBMoviePage;
Movies | TTMDBMovieDetail | Translations | ITMDBTranslations | TEST | AppendedTranslations | function AppendedTranslations: ITMDBTranslations; stdcall; | function TTTMDBMovieDetail.AppendedTranslations: ITMDBTranslations;
Movies | TTMDBMovieDetail | Videos | ITMDBVideos | DONE | AppendedVideos | function AppendedVideos: ITMDBVideos; stdcall; | function TTTMDBMovieDetail.AppendedVideos: ITMDBVideos;
People | TTMDBPersonDetail | Changes | ITMDBChanges | TEST | AppendedChanges | function AppendedChanges: ITMDBChanges; stdcall; | function TTTMDBPersonDetail.AppendedChanges: ITMDBChanges;
People | TTMDBPersonDetail | CombinedCredits | ITMDBCombinedCredits | TEST | AppendedCombinedCredits | function AppendedCombinedCredits: ITMDBCombinedCredits; stdcall; | function TTTMDBPersonDetail.AppendedCombinedCredits: ITMDBCombinedCredits;
People | TTMDBPersonDetail | ExternalIDs | ITMDBExternalIDs | TEST | AppendedExternalIDs | function AppendedExternalIDs: ITMDBExternalIDs; stdcall; | function TTTMDBPersonDetail.AppendedExternalIDs: ITMDBExternalIDs;
People | TTMDBPersonDetail | Images | ITMDBMediaImageGroup | TEST | AppendedImages | function AppendedImages: ITMDBMediaImageGroup; stdcall; | function TTTMDBPersonDetail.AppendedImages: ITMDBMediaImageGroup;
People | TTMDBPersonDetail | MovieCredits | ITMDBCombinedCredits | TEST | AppendedMovieCredits | function AppendedMovieCredits: ITMDBCombinedCredits; stdcall; | function TTTMDBPersonDetail.AppendedMovieCredits: ITMDBCombinedCredits;
People | TTMDBPersonDetail | TVCredits | ITMDBCombinedCredits | TEST | AppendedTVCredits | function AppendedTVCredits: ITMDBCombinedCredits; stdcall; | function TTTMDBPersonDetail.AppendedTVCredits: ITMDBCombinedCredits;
People | TTMDBPersonDetail | Translations | ITMDBTranslations | TEST | AppendedTranslations | function AppendedTranslations: ITMDBTranslations; stdcall; | function TTTMDBPersonDetail.AppendedTranslations: ITMDBTranslations;
TV Series | TTMDBTVSerieDetail | AccountStates | ITMDBAccountStates | DONE | AppendedAccountStates | function AppendedAccountStates: ITMDBAccountStates; stdcall; | function TTTMDBTVSerieDetail.AppendedAccountStates: ITMDBAccountStates;
TV Series | TTMDBTVSerieDetail | AggregateCredits | ITMDBAggregateCredits | TEST | AppendedAggregateCredits | function AppendedAggregateCredits: ITMDBAggregateCredits; stdcall; | function TTTMDBTVSerieDetail.AppendedAggregateCredits: ITMDBAggregateCredits;
TV Series | TTMDBTVSerieDetail | AlternativeTitles | ITMDBAlternativeTitles | DONE | AppendedAlternativeTitles | function AppendedAlternativeTitles: ITMDBAlternativeTitles; stdcall; | function TTTMDBTVSerieDetail.AppendedAlternativeTitles: ITMDBAlternativeTitles;
TV Series | TTMDBTVSerieDetail | Changes | ITMDBChanges | TEST | AppendedChanges | function AppendedChanges: ITMDBChanges; stdcall; | function TTTMDBTVSerieDetail.AppendedChanges: ITMDBChanges;
TV Series | TTMDBTVSerieDetail | ContentRatings | ITMDBContentRatings | TEST | AppendedContentRatings | function AppendedContentRatings: ITMDBContentRatings; stdcall; | function TTTMDBTVSerieDetail.AppendedContentRatings: ITMDBContentRatings;
TV Series | TTMDBTVSerieDetail | Credits | ITMDBCredits | DONE | AppendedCredits | function AppendedCredits: ITMDBCredits; stdcall; | function TTTMDBTVSerieDetail.AppendedCredits: ITMDBCredits;
TV Series | TTMDBTVSerieDetail | EpisodeGroups | ITMDBEpisodeGroups | TEST | AppendedEpisodeGroups | function AppendedEpisodeGroups: ITMDBEpisodeGroups; stdcall; | function TTTMDBTVSerieDetail.AppendedEpisodeGroups: ITMDBEpisodeGroups;
TV Series | TTMDBTVSerieDetail | ExternalIDs | ITMDBExternalIDs | TEST | AppendedExternalIDs | function AppendedExternalIDs: ITMDBExternalIDs; stdcall; | function TTTMDBTVSerieDetail.AppendedExternalIDs: ITMDBExternalIDs;
TV Series | TTMDBTVSerieDetail | Images | ITMDBMediaImageGroup | DONE | AppendedImages | function AppendedImages: ITMDBMediaImageGroup; stdcall; | function TTTMDBTVSerieDetail.AppendedImages: ITMDBMediaImageGroup;
TV Series | TTMDBTVSerieDetail | Keywords | ITMDBKeywords | TEST | AppendedKeywords | function AppendedKeywords: ITMDBKeywords; stdcall; | function TTTMDBTVSerieDetail.AppendedKeywords: ITMDBKeywords;
TV Series | TTMDBTVSerieDetail | Lists | ITMDBListPage | TEST | AppendedLists | function AppendedLists: ITMDBListPage; stdcall; | function TTTMDBTVSerieDetail.AppendedLists: ITMDBListPage;
TV Series | TTMDBTVSerieDetail | Recommendations | ITMDBMediaPage | TEST | AppendedRecommendations | function AppendedRecommendations: ITMDBMediaPage; stdcall; | function TTTMDBTVSerieDetail.AppendedRecommendations: ITMDBMediaPage;
TV Series | TTMDBTVSerieDetail | Reviews | ITMDBReviewPage | DONE | AppendedReviews | function AppendedReviews: ITMDBReviewPage; stdcall; | function TTTMDBTVSerieDetail.AppendedReviews: ITMDBReviewPage;
TV Series | TTMDBTVSerieDetail | ScreenedTheatrically | ITMDBScreenedTheatricallyItems | TEST | AppendedScreenedTheatrically | function AppendedScreenedTheatrically: ITMDBScreenedTheatricallyItems; stdcall; | function TTTMDBTVSerieDetail.AppendedScreenedTheatrically: ITMDBScreenedTheatricallyItems;
TV Series | TTMDBTVSerieDetail | Similar | ITMDBTVSeriesPage | TEST | AppendedSimilar | function AppendedSimilar: ITMDBTVSeriesPage; stdcall; | function TTTMDBTVSerieDetail.AppendedSimilar: ITMDBTVSeriesPage;
TV Series | TTMDBTVSerieDetail | Translations | ITMDBTranslations | TEST | AppendedTranslations | function AppendedTranslations: ITMDBTranslations; stdcall; | function TTTMDBTVSerieDetail.AppendedTranslations: ITMDBTranslations;
TV Series | TTMDBTVSerieDetail | Videos | ITMDBVideos | DONE | AppendedVideos | function AppendedVideos: ITMDBVideos; stdcall; | function TTTMDBTVSerieDetail.AppendedVideos: ITMDBVideos;
TV Seasons | ITMDBTVSeasonDetail | AccountStates | ITMDBAccountStates | TEST | AppendedAccountStates | function AppendedAccountStates: ITMDBAccountStates; stdcall; | function TITMDBTVSeasonDetail.AppendedAccountStates: ITMDBAccountStates;
TV Seasons | ITMDBTVSeasonDetail | AggregateCredits | ITMDBAggregateCredits | TEST | AppendedAggregateCredits | function AppendedAggregateCredits: ITMDBAggregateCredits; stdcall; | function TITMDBTVSeasonDetail.AppendedAggregateCredits: ITMDBAggregateCredits;
TV Seasons | ITMDBTVSeasonDetail | Changes | ITMDBChanges | TEST | AppendedChanges | function AppendedChanges: ITMDBChanges; stdcall; | function TITMDBTVSeasonDetail.AppendedChanges: ITMDBChanges;
TV Seasons | ITMDBTVSeasonDetail | Credits | ITMDBCredits | TEST | AppendedCredits | function AppendedCredits: ITMDBCredits; stdcall; | function TITMDBTVSeasonDetail.AppendedCredits: ITMDBCredits;
TV Seasons | ITMDBTVSeasonDetail | ExternalIDs | ITMDBExternalIDs | TEST | AppendedExternalIDs | function AppendedExternalIDs: ITMDBExternalIDs; stdcall; | function TITMDBTVSeasonDetail.AppendedExternalIDs: ITMDBExternalIDs;
TV Seasons | ITMDBTVSeasonDetail | Images | ITMDBMediaImageGroup | TEST | AppendedImages | function AppendedImages: ITMDBMediaImageGroup; stdcall; | function TITMDBTVSeasonDetail.AppendedImages: ITMDBMediaImageGroup;
TV Seasons | ITMDBTVSeasonDetail | Translations | ITMDBTranslations | TEST | AppendedTranslations | function AppendedTranslations: ITMDBTranslations; stdcall; | function TITMDBTVSeasonDetail.AppendedTranslations: ITMDBTranslations;
TV Seasons | ITMDBTVSeasonDetail | Videos | ITMDBVideos | TEST | AppendedVideos | function AppendedVideos: ITMDBVideos; stdcall; | function TITMDBTVSeasonDetail.AppendedVideos: ITMDBVideos;
TV Episodes | ITMDBTVEpisodeDetail | AccountStates | ITMDBAccountStates | TEST | AppendedAccountStates | function AppendedAccountStates: ITMDBAccountStates; stdcall; | function TITMDBTVEpisodeDetail.AppendedAccountStates: ITMDBAccountStates;
TV Episodes | ITMDBTVEpisodeDetail | Changes | ITMDBChanges | TEST | AppendedChanges | function AppendedChanges: ITMDBChanges; stdcall; | function TITMDBTVEpisodeDetail.AppendedChanges: ITMDBChanges;
TV Episodes | ITMDBTVEpisodeDetail | Credits | ITMDBCredits | TEST | AppendedCredits | function AppendedCredits: ITMDBCredits; stdcall; | function TITMDBTVEpisodeDetail.AppendedCredits: ITMDBCredits;
TV Episodes | ITMDBTVEpisodeDetail | ExternalIDs | ITMDBExternalIDs | TEST | AppendedExternalIDs | function AppendedExternalIDs: ITMDBExternalIDs; stdcall; | function TITMDBTVEpisodeDetail.AppendedExternalIDs: ITMDBExternalIDs;
TV Episodes | ITMDBTVEpisodeDetail | Images | ITMDBMediaImageGroup | TEST | AppendedImages | function AppendedImages: ITMDBMediaImageGroup; stdcall; | function TITMDBTVEpisodeDetail.AppendedImages: ITMDBMediaImageGroup;
TV Episodes | ITMDBTVEpisodeDetail | Translations | ITMDBTranslations | TEST | AppendedTranslations | function AppendedTranslations: ITMDBTranslations; stdcall; | function TITMDBTVEpisodeDetail.AppendedTranslations: ITMDBTranslations;
TV Episodes | ITMDBTVEpisodeDetail | Videos | ITMDBVideos | TEST | AppendedVideos | function AppendedVideos: ITMDBVideos; stdcall; | function TITMDBTVEpisodeDetail.AppendedVideos: ITMDBVideos;